- Step overview

| Sub-area | 7.2. Digitalisation |
| --- | --- |
| Reform | 7.2.4. Setting-up a comprehensive framework for cyber resilience and artificial intelligence Part 2: Setting up the legal framework for Artificial Intelligence |
| Reporting indicator | Extent to which a comprehensive framework for cyber resilience in line with requirements of NIS2 Directive is set up and operational |
| Reform Step | 1. The Law on Artificial Intelligence is adopted, based on a high-risk approach, and with the necessary enforcement structures in place |
| Step deadline | December 2025 |
| Step value in EUR | 13.587.623,37 |
| Responsible | Ministry of Science, Technological Development and Innovation |
| Baseline | AI regulation is not adopted |
| Sources of verification | Report of Office for IT and eGovernment and/or Ministry of Information and Telecommunications |

- Analysis

| Define step milestones | For each step, based on the provisions of the Reform Agenda, define several key milestones for full achievement and number them. E.g. for a legislative step, that can include: 1. Announcement of the work on the new law, 2. Setting up a working group, 3. Initial consultation (via eConsultation portal), 4. Publication of all key materials on eConsultation portal (draft law, RIA, consultation report), 5. Public debate in accordance with the Rules of Procedure of the Government, 6. Adoption in Parliament (with analysis of the adoption procedure). Depending on the reform step, make sure that milestones take into account applicable legal requirements (e.g. Law on the Planning System, Government Rules of Procedure, etc.). 1. Announcement of work on the new law on the eConsultation portal and/ or Ministry website. 2. Establishment of the working group through an open process, an open call for civil society organizations to participate 3. (Early) Consultation conducted via eConsultation Portal 4. Publication of the draft law on the eConsultation Portal 5. Public debate conducted in accordance with procedures 6. Consultation and public debate report(s) published on the eConsultation Portal, along with the final version of the draft law 7. Adoption of the draft law at a government session 8. The proposed law was presented and discussed in the relevant parliamentary committee(s) 9. The proposed law was presented and discussed at a plenary session of Parliament 10. Parliament adopted the proposed law in compliance with all required procedures. |
| --- | --- |
| Analyse achievement of each milestone | For each identified milestone, provide a succinct analysis of its implementation process. Use numbered points corresponding to the defined milestones above. Please provide references wherever possible. - The commencement of work on the Draft Law on Artificial Intelligence was initially announced on the eConsultation Portal in 2024, marking the first attempt to initiate the drafting process. However, this process was discontinued in 2025 following the formation of the new Government. A renewed initiative to prepare the law was subsequently announced at the Trilateral Meeting (Government – DEU – NCEU) on the Reform Agenda Implementation Monitoring, held on 1 December 2025. Indications that the process has resumed include direct invitations sent in January 2026 to two civil society organisations to participate in the Working Group. Nevertheless, at the time of drafting this report (March 2026), no official information on the re-initiation of the drafting process has been published on the eConsultation Portal. - No open call for participation was issued. The first Working group tasked with drafting the Law on Artificial Intelligence was formed in August 2024 by the Ministry of Science, Technological Development, and Innovation. It should be noted, however, that the Decision of the Ministry on forming the group is dated 28 August 2024, though the public statement announcement on the first WG meeting was published on the Ministry’s website and dated 31st May 2024. The public was informed about the process primarily through media coverage and the announcement published on the eConsultation Portal, without any accompanying documentation. The Working Group was established on an invitation-only basis, with no public call for participation, which had implications for its composition. Although it included representatives of state institutions, the business sector, academia, and the corporate legal community, civil society representation was notably limited, with only two out of 45 members coming from civil society organisations (NALED and the SHARE Foundation). Following the election of the new Government by the Parliament of Serbia in April 2025, the Working Group suspended its activities. In January 2026, the Ministry of Science, Technological Development and Innovation initiated the process of establishing a new Working Group. At the time of drafting this report (March 2026), there is no publicly available information confirming whether the new Working Group has been formally established. The information on the initiation of this process is based on the announcement made at the Trilateral Meeting (Government – DEU – NCEU) on the Reform Agenda Implementation Monitoring held on 1 December 2025, as well as on the fact that two civil society organisations, members of the National Convention on the European Union, received direct invitations to participate in the Working Group in January 2026. No open call for participation was issued. No further steps have been made in relation to the adoption of this law, so we cannot report on other milestones. |
| Key issues in implementation | List and briefly explain key problems/issues arising in the reform step implementation. This can follow the milestone structure, but depending on the reform step, it can also be an analysis for the whole step. Please provide references wherever possible. The process of establishing both Working Groups was marked by limited transparency and inclusiveness. The formation of both Working Groups tasked with drafting the Law on Artificial Intelligence did not involve a public call, nor was information on the process or any baseline analysis made available on the eConsultation Portal or the Ministry’s website. The first Working Group was constituted through direct invitations to pre-selected institutions, organisations, and corporate entities. The second Working Group was established in a similar manner. Furthermore, the composition of the 2024 Working Group did not reflect the diversity of stakeholders that should be involved in such a process. Notably, only two out of 45 members represented civil society. The composition of the newly established Working Group has not yet been publicly disclosed. |
| Analyse how key principles of RGF were respected in the reform step implementation | How transparent has the reform step implementation been? How has civil society and the wider public been informed about it? What data and information, including key documents, have been made publicly available? How inclusive was the implementation process? Has the implementation of the reform step allowed for participation of interested stakeholders, especially civil society organisations and – where applicable – business community? How was such participation ensured? What were the issues regarding their participation, if any? Depending on the reform step, provide an analysis of how other key RGF principles – apart from transparency and inclusivity analysed above – were respected in its implementation, as applicable: sound financial management, equal treatment, non-discrimination and proportionality for intended purpose. Please provide references wherever possible. Transparency The process of establishing and operating the Working Groups was characterized by limited transparency. Although the initiation of the drafting process was announced through the media and the eConsultation Portal when the work of the first Working Group began, no supporting documentation, background analyses, or updates on its progress were made publicly available. Key procedural steps, including the re-initiation of the process in January 2026, were not formally communicated through the eConsultation Portal or any other official channel. Information on the formation of the new Working Group, its membership, or any related documents is not publicly available. Inclusiveness The process of forming the Working Groups was not sufficiently inclusive. Both Working Groups were established without public calls for participation, relying instead on direct invitations to pre-selected stakeholders. This approach limited the opportunity for broader participation, particularly from civil society. As a result, the composition of the 2024 Working Group reflected a narrow stakeholder base, with only two out of 45 members representing civil society organisations. The same pattern appears to have been repeated in the 2026 process, further restricting diverse and balanced stakeholder involvement. |
| Public availability of evidence of implementation | Has the final source of verification (as per Reform Agenda) been made publicly available? If yes, please list the source (provide link) and date. N/A |
| Analyse quality of the final output of the reform step | To what extent does the final output of this reform step respect the applicable EU membership requirements/principles/standards? No final output |

- Final assessment

| Assess formal achievement | Not achieved |
| --- | --- |
| Elaboration of final assessment | The deadline for the adoption of the Law on Artificial Intelligence was set in the Reform Agenda for December 2025. The Law was not adopted, nor any draft was published or made available to the public. The Working group tasked with drafting the Law was formed in an untransparent manner, without a public call. |

The first attempt at drafting the AI Law was stopped; the eConsultation link is not available anymore.

The National Alliance for Local Economic Development (NALED) and Partners for Democratic Change of Serbia.

The first attempt at drafting the AI Law was stopped; the eConsultation link is not available anymore.