- Step overview

| Sub-area | 7.2. Digitalisation |
| --- | --- |
| Reform | 7.2.4. Setting-up a comprehensive framework for cyber resilience and artificial intelligence Part 1: Improving the legal framework for cybersecurity (introducing requirements of NIS2 Directive and strengthening relevant institutions) |
| Reporting indicator | Extent to which a comprehensive framework for cyber resilience in line with requirements of NIS2 Directive is set up and operational |
| Reform Step | 4. List of entities in the scope of the national law corresponding to the NIS2 Directive is finalized and Frameworks introduced by NIS2 alignment (CVD framework, crisis management framework), are in place and use |
| Step deadline | December 2025 |
| Step value in EUR | 3.396.905,84 |
| Responsible | Ministry of Information and Telecommunications |
| Baseline | List of entities in scope of the national law corresponding to the NIS2 Directive is NOT prepared and Frameworks NOT introduced by NIS2 alignment (CVD framework, crisis management |
| Sources of verification | Report of Ministry of Information and Telecommunications |

- Analysis

| Define step milestones | For each step, based on the provisions of the Reform Agenda, define several key milestones for full achievement and number them. E.g. for a legislative step, that can include: 1. Announcement of the work on the new law, 2. Setting up a working group, 3. Initial consultation (via eConsultation portal), 4. Publication of all key materials on eConsultation portal (draft law, RIA, consultation report), 5. Public debate in accordance with the Rules of Procedure of the Government, 6. Adoption in Parliament (with analysis of the adoption procedure). Depending on the reform step, make sure that milestones take into account applicable legal requirements (e.g. Law on the Planning System, Government Rules of Procedure, etc.). - List of entities finalized - CVD framework in place and used - Crisis-management framework in place and used |
| --- | --- |
| Analyse achievement of each milestone | For each identified milestone, provide a succinct analysis of its implementation process. Use numbered points corresponding to the defined milestones above. Please provide references wherever possible. - Under the 2025 Law, finalising the NIS2-equivalent “scope list” depends on adopting the Government bylaw on general/sectoral criteria for determining priority and important entities and operationalising the Ministry-led Evidence (registry). In the Ministry’s FOI reply from 6 March 2026, the key criteria bylaw is reported as in the adoption procedure, while other necessary implementing acts (including the Evidence rulebook) are not yet adopted (some only “expected to start”). - The Law introduces a vulnerability-handling layer by assigning the national CERT function the task of maintaining a vulnerability database and by requiring Government-level implementing rules to operationalise key procedures. According to the same FOI reply (6 March 2026), the main bylaw on the content and verification procedure for vulnerabilities is still in drafting, which means the CVD framework cannot yet be considered “in place”; moreover, no publicly evidenced use is demonstrated through adopted implementing acts. - The Law requires a Government bylaw regulating incident notification procedures, forms, incident lists and severity classification, and a Government crisis response plan for high-level incidents and information-security crises, with an explicit deadline of 18 months from the Law’s entry into force (and a 12-month deadline for other implementing acts). The Ministry’s FOI reply (6 March 2026) indicates that the relevant implementing acts are not yet adopted (some only “expected to start”), therefore the crisis-management framework cannot yet be assessed as “in place and in use”. |
| Key issues in implementation | List and briefly explain key problems/issues arising in the reform step implementation. This can follow the milestone structure, but depending on the reform step, it can also be an analysis for the whole step. Please provide references wherever possible. Implementation of Reform Step 2.2.4.2 is effectively stalled at the level of deliverables: the “list of entities” cannot be finalised because the core implementing acts required by the Law (Government bylaw on scoping criteria and the Ministry rulebook on the Evidence) have not been adopted; the CVD framework is not “in place and in use” because the Government act regulating the vulnerability database and verification/handling procedures is still pending; and the crisis-management framework is not “in place and in use” because the implementing rules on incident notification/classification and the Government crisis response plan have not been adopted/published. As a result, none of the three Reform Step outcomes can be publicly verified as achieved on the basis of adopted secondary legislation and operational evidence. |
| Analyse how key principles of RGF were respected in the reform step implementation | How transparent has the reform step implementation been? How has civil society and the wider public been informed about it? What data and information, including key documents, have been made publicly available? How inclusive was the implementation process? Has the implementation of the reform step allowed for participation of interested stakeholders, especially civil society organisations and – where applicable – business community? How was such participation ensured? What were the issues regarding their participation, if any? Depending on the reform step, provide an analysis of how other key RGF principles – apart from transparency and inclusivity analysed above – were respected in its implementation, as applicable: sound financial management, equal treatment, non-discrimination and proportionality for intended purpose. Please provide references wherever possible. No information, as Ministry stated that all 3 documents are still in “expected to start” phase. |
| Public availability of evidence of implementation | Has the final source of verification (as per Reform Agenda) been made publicly available? If yes, please list the source (provide link) and date. No source of verification. |
| Analyse quality of the final output of the reform step | To what extent does the final output of this reform step respect the applicable EU membership requirements/principles/standards? No final output. |

- Final assessment

| Assess formal achievement | Not achieved |
| --- | --- |
| Elaboration of final assessment | Not achieved, because none of the three required outcomes (milestones) is in place in a verifiable manner: the list of entities cannot be finalised without the adopted implementing acts for scoping criteria and the Evidence/registry, and both the CVD and crisis-management frameworks depend on secondary legislation and operational instruments that have not been adopted/published. Consequently, there is no public evidence that these frameworks are operational and used, as required by the Reform Agenda. |