7.1.1. Implementation of the 3rd Energy Package for gas, and of the electricity integration package

| Sub-area | 7.1. Energy sector transformation |
| --- | --- |
| Reform | 7.1.1. Implementation of the 3rd Energy Package for gas, and of the electricity integration package |
| Reporting indicator | Status of legal and regulatory framework |
| Reform Step | - Allocation of capacities at Horgos and IBS border points is opened |
| Step deadline | June 2025 |
| Step value in EUR | 20,381,435.06 |
| Responsible | Ministry of Mining and Energy and Energy Agency of the Republic of Serbia (AERS) |
| Baseline | Rules on the Operation of the Transport System submitted to the Energy Agency of the Republic of Serbia by "Transportgas Srbija" for approval. |
| Sources of verification | Report of TSO |

# Analysis

| Define step milestones | - Regulatory framework for capacity allocation exists and is approved (Energy Law duties, adopted network code and TSO operational rules). - Technical readiness & operational preconditions, including the IBS infrastructure permit/license milestone (use permit) and functioning platform tooling. - Publication of the allocation procedure (products, platforms, deadlines, and result publication) - Annual capacity allocation process is launched and results published (including dates and rule-basis), with the Interconnection points and capacity information published - Allocation is opened at the specific border points (Horgoš and IBS) in a manner consistent with non-discrimination and Energy Community acquis. |
| --- | --- |
| Analyse achievement of each milestone | For each identified milestone, provide a succinct analysis of its implementation process. Use numbered points corresponding to the defined milestones above. Please provide references wherever possible. - Transportgas adopted network rules governing access and capacity allocation and submitted them for regulatory consent. AERS confirms the timeline: draft submitted 28 January 2025, preceded by public consultation from 9 August to 9 September 2024, and AERS formally granted consent on 30 January 2025. - A key infrastructural prerequisite is the legal permissibility of operating the IBS gas interconnector as an entry into the Serbian network. Transportgas reports confirm that the MG‑10 Niš–Dimitrovgrad pipeline (Serbia–Bulgaria interconnector) was in trial operation (Dec 2023–Dec 2024) and obtained a use permit on 14 January 2025 from Ministry of Construction, Transport and Infrastructure, including the exact reference: ROP‑MSGI‑40633‑IUPH‑2/2024; number 003451581 2024 14810 005 001 000 001. Transportgas further states that this enabled a new cross-border entry “Bulgaria/Serbia” into the transmission system. In parallel, technical readiness for running allocations is evidenced by the existence of the public User Platform portal with modules for “Calls” and documentation downloads. - This milestone tests whether a transparent allocation procedure was published (not only performed). Evidence shows three distinct layers: - Network rules provide the legal-procedural backbone. Transportgas rules define an “Auction Calendar” as a pre-defined schedule of auctions for standard capacity products at interconnection points, published by ENTSO-G on its official website. The rules also specify operational mechanics: users must demonstrate “readiness to pay” by submitting payment security instruments before allocation begins, and the TSO communicates acceptance/ contracting electronically. Crucially, section 11.9 imposes transparency duties: the TSO must publish aggregated data on allocation results and specifies publication timing. - User Platform calendar publicly specifies deadlines and product types. The User Platform “Calendar” page for gas year 2026/27 provides a clear, user-facing schedule distinguishing interconnection points vs other points, including: annual firm capacity on interconnection points aligned with ENTSO-G calendar, on the first Monday in July for the next five gas years, with results published the next working day; analogous schedules for quarterly, monthly, daily, and intraday products. - User Platform Guideline document concrete user actions. The User Platform Guideline describes how users view “Calls,” see deadlines, submit capacity requests, track statuses, and finalize submission, including how approved capacity becomes visible after allocation and how payment security instruments relate to interconnection points. - Transportgas’ capacity allocation platform states that aggregated annual capacity allocation results at interconnection points were published, covering gas years 2026–2030, conducted via the Transportgas operational platform aligned with the ENTSOG auction calendar, with the offer period 6 June-7 July, 2025 and allocation completion 8 July 2025. Public evidence confirms that key entry points (including Horgoš and the Bulgaria-related entry point referenced domestically as “Kalotina/Dimitrovgrad”) are treated as interconnection-related entry points in Transportgas reporting. The Transportgas Report on non-discriminatory behaviour (2024 reporting) references entry points including “U1 – PPS Horgos” and “U2 – IP Kalotina/Dimitrovgrad” and describes constraints on offering capacity beyond transit/limited conditions in 2024. - Transportgas published aggregated results as a transparency action and states it is doing so under the Energy Law and its network rules (explicitly referencing Article 248 and rule section 11.9). It states the annual allocation results for gas years 2025–2030 were processed and that allocation was completed on 8 July 2025. Many of the issues from 2024 were fixed with the introduction of Transportgas’ booking platform, with rules and guidelines. However, both the EU Commission report and Energy Community Implementation Report for 2025 state that the level of open allocation is not sufficient, mostly due to the lack of user-friendly interface of the booking platform. For that reason, the allocation of capacities at these two IPS were opened in 2025, but not fully aligned with the Energy Community Acquis. |
| Key issues in implementation | The central issue is the gap between formal opening and effective market functioning. While allocation has been opened, this does not necessarily ensure that capacity is widely accessible, competitively used, or efficiently allocated in practice. A second issue concerns incomplete alignment in implementation across borders. Even though the regulatory framework is largely aligned with EU rules, practical coordination with neighbouring systems and full application of capacity allocation mechanisms remain inconsistent. Operationalization and participation of the Transportgas Srbija in the Regional Booking Platform would possibly fix this issue. A third issue relates to transparency. While the allocation mechanism is publicly accessible, detailed and systematic data on allocation outcomes is not always fully available, limiting external verification of market performance. Also, in the TSO report for 2024, it was clearly stated that the main issue of implementation was the lack of national dedicated booking platform. This was fixed in 2025, but the platform is still not operationalized fully, as noted in the Energy Community Implementation Report for 2025. Opening capacities is not only running a process, but also offering meaningful capacity volumes to third parties at the strategic entry points. Both EU and Energy Community monitoring explicitly frame this as incomplete even after IBS began commercial operations in 2025. |
| Analyse how key principles of RGF were respected in the reform step implementation | Transparency Transportgas publishes an allocation notice with dates, legal basis references, and a downloadable result table. External monitors nonetheless consider transparency and usability insufficient at interconnection points. Inclusivity Public consultation evidence exists for related codes (AERS network code hearing), conducted from 9 August to 9 September, 2024, but for the specific Horgoš/IBS allocation opening, inclusivity is less relevant than transparency and equal treatment. Proportionality for intended purpose An annual allocation mechanism aligned with ENTSO-G calendars is proportionate and consistent with EU network code logic. The unresolved issue is not disproportional measures, but incomplete effect. Equal treatment / non‑discrimination Energy Community language indicates persistent deficits in non-discriminatory openness of allocation/TPA, which is directly contrary to the intended principle. |
| Public availability of evidence of implementation | Has the final source of verification (as per Reform Agenda) been made publicly available? If yes, please list the source (provide link) and date. Publicly available: YES, although not as listed in the Reform Agenda. The main issue was lack of Report of TSO on non-discriminatory measures for 2025, which is expected later in 2026 (the Report for 2024 was published in November, 2025). Source: - Government of the Republic of Serbia - AERS - Energy Community Secretariate Link: - https://www.paragraf.rs/propisi/zakon_o_energetici.html - https://www.transportgas-srbija.rs/sr/pristup-sistemu/pravila-o-radu-transportnog-sistema - https://api.transportgas-srbija.rs/assets/godisnji-izvestaj-za-nediskriminatorno-ponasanje-za-2024.-godinu.pdf - https://www.energy-community.org/dam/jcr:5b4ff2d5-5672-4989-ad81-d7fd9e27a7f7/Serbia_IR25CP.pdf - https://api.transportgas-srbija.rs/assets/korisnicko-uputstvo---za-korisnika.pdf - https://kp.transportgas-srbija.com/capacity-allocation - https://kp.transportgas-srbija.com/OfferView - https://www.transportgas-srbija.rs/vesti/obavestenje-o-zapocinjanju-javnix-konsultacija-vezano-za-nacrt-pravila-o-radu-transportnog-sistema-transportgas-srbija-doo-i-nacrta-modela-ugovora-o-transportu-prirodnog-gasa - https://api.transportgas-srbija.rs/assets/izvestaj-sa-javne-konsultacije-vezane-za-nacrt-pravila-o-radu-transportnog-sistema-transportgas-srbija.doc Date of publication: - 1) November, 2024 - 2) January, 2025 - 3) November, 2025. - 4) December, 2025 - 5)-7) Accessed February 26, 2026. - 8) August, 2024. - 9) September, 2024 |
| Analyse quality of the final output of the reform step | The quality benchmark is EU/Energy Community acquis: “open capacity allocation on a non-discriminatory basis” coupled with effective TPA. The European Commission explicitly states this remains to be fully implemented for IBS in line with the Energy Community acquis and Serbia’s Reform Agenda commitments, which directly implies the output is not yet fully aligned to accession expectations. |

# Final assessment

| Assess formal achievement | Not achieved |
| --- | --- |
| Elaboration of final assessment | While a platform-based annual allocation cycle is evidenced and aligned with ENTSO-G calendar logic, the step’s substance is opening capacities at Horgoš and IBS in a non-discriminatory, open manner. EU and Energy Community monitoring still describe open capacity allocation and unrestricted TPA as pending even after IBS commercial operations began, due to the lack of operationalization of the Transportgas Srbija booking platform. Further development of the platform and the participation of TSO in the Regional Booking Platform should fix this issue. We therefore consider this reform step as not achieved, but with significant progress made in the reporting period. |

https://api.transportgas-srbija.rs/assets/pravila-o-radu-transportnog-sistema-prirodnog-gasa-transportgas-srbija-doo-novi-sad.pdf (accessed on 26 February, 2026).

https://www.transportgas-srbija.rs/vesti/obavestenje-o-zapocinjanju-javnix-konsultacija-vezano-za-nacrt-pravila-o-radu-transportnog-sistema-transportgas-srbija-doo-i-nacrta-modela-ugovora-o-transportu-prirodnog-gasa; Report of the results of public consultations is available here: https://api.transportgas-srbija.rs/assets/izvestaj-sa-javne-konsultacije-vezane-za-nacrt-pravila-o-radu-transportnog-sistema-transportgas-srbija.doc (accessed on 26 February, 2026).

https://api.transportgas-srbija.rs/assets/odluka-saveta-agencije-za-energetiku-republike-srbije-odavanju-saglasnosti-na-pravila-o-radu-(1).pdf (accessed on 26 February, 2026).

https://api.transportgas-srbija.rs/assets/godisnji-izvestaj-za-nediskriminatorno-ponasanje-za-2024.-godinu.pdf (accessed on 26 February,2026).

https://kp.transportgas-srbija.com/ (accessed on 26 February, 2026).

https://api.transportgas-srbija.rs/assets/pravila-o-radu-transportnog-sistema-prirodnog-gasa-transportgas-srbija-doo-novi-sad.pdf (accessed on 26 February, 2026).

https://www.gasconnect.at/en/recent/news/detail/entsog-publishes-auction-calendar-for-2025-2026 (accessed on 26 February, 2026).

https://kp.transportgas-srbija.com/Calendar (accessed on 26 February, 2026).

https://kp.transportgas-srbija.com/capacity-allocation (accessed on 26 February, 2026).

https://kp.transportgas-srbija.com/api/FileDownload/%D0%9A%D0%BE%D1%80%D0%B8%D1%81%D0%BD%D0%B8%D1%87%D0%BA%D0%BE%20%D1%83%D0%BF%D1%83%D1%82%D1%81%D1%82%D0%B2%D0%BE%20-%20%D0%97%D0%B0%20%D0%BA%D0%BE%D1%80%D0%B8%D1%81%D0%BD%D0%B8%D0%BA%D0%B0.pdf?path=Helpers/UserManual (accessed on 26 February, 2026).

https://kp.transportgas-srbija.com/capacity-allocation (accessed on 26 February, 2026).

https://api.transportgas-srbija.rs/assets/godisnji-izvestaj-za-nediskriminatorno-ponasanje-za-2024.-godinu.pdf (accessed on 26 February, 2026).

https://kp.transportgas-srbija.com/capacity-allocation (accessed on 26 February, 2026).

https://www.energy-community.org/dam/jcr:5b4ff2d5-5672-4989-ad81-d7fd9e27a7f7/Serbia_IR25CP.pdf (accessed on 26 February, 2026).

Ibidem.

https://www.transportgas-srbija.rs/vesti/obavestenje-o-zapocinjanju-javnix-konsultacija-vezano-za-nacrt-pravila-o-radu-transportnog-sistema-transportgas-srbija-doo-i-nacrta-modela-ugovora-o-transportu-prirodnog-gasa; Report of the results of public consultations is available here: https://api.transportgas-srbija.rs/assets/izvestaj-sa-javne-konsultacije-vezane-za-nacrt-pravila-o-radu-transportnog-sistema-transportgas-srbija.doc (accessed on 26 February, 2026).