7.1.6 Implementation of MRVA

| Sub-area | 7.1. Energy sector transformation |
| --- | --- |
| Reform | 7.1.6 Implementation of MRVA |
| Reporting indicator | Degree of implementation of MRVA legislative and regulatory framework, assessed by the number of issued permits (with approved monitoring plans) |
| Reform Step | - Competent authority [for the implementation of the rules of the ETS Directive] approves monitoring plans [in line with national legislation that transposes the Commission Implementing Regulation [EU] 2018/2066 [MMRR]] |
| Step deadline | December 2025 |
| Step value in EUR | 6,793,811.69 |
| Responsible | Ministry of Environmental Protection (Competent Authority) |
| Baseline | Legislation that transposes MRVA acquis recently adopted: Law on Climate Change (“Official Gazette of the RS”, No 26/21), Regulation on types of activities and greenhouse gases („Official Gazette of the Republic of Serbia“, No. 13/2022), Rulebook on the verification and accreditation of verifiers of reports on greenhouse gas emissions („Official Gazette of the Republic of Serbia“, no. 107/21), Rulebook on the monitoring and reporting of greenhouse gas emissions ("Official Gazette of the Republic of Serbia“, no. 118/23) or 0 GHG permits issued (GHG permit is an act by which the Competent Authority approves the Monitoring Plan. |
| Sources of verification | Registry of issued GHG permits published at official MoEP website, or a specially designated website. |

# Analysis

| Define step milestones | Since the legal framework has been established in the baseline, consisting of Climate Change Law and enabling by‑laws covering: (a) scope (activities and gases), (b) monitoring/reporting rules aligned to MMRR, (c) verification/accreditation rules, it is necessary to further implement and operationalize all components of the MRVA system. For that reason, the following milestones are defined: - Operational readiness of the MRVA system established; - Issuance of GHG permits with approved monitoring plans; - Verification and accreditation system operational; - Public registry of issued GHG permits available. |
| --- | --- |
| Analyse achievement of each milestone | - Operational readiness of the MRVA system established: The competent authority designated under the Law on Climate Change, the Ministry of Environmental Protection, is operational and applies procedures for the review of monitoring plans. The eGHG digital platform functions as the official system for submission and processing of monitoring plans and issuance of GHG permits. Training and guidance activities for covered operators and relevant institutions have been conducted. - Issuance of GHG permits with approved monitoring plans; The process of issuance of GHG emission permits was initiated in October 2024. So far, a total of 97 permits with approved monitoring plan were issued. - Verification and accreditation system operational; The system for verification and accreditation of verifiers is operational, in line with the national transposition of Regulation (EU) 2018/2067. The Accreditation Body of Serbia performs accreditation of verification bodies for GHG emission reports, ensuring full implementation of MRVA cycle. So far, 5 verifiers have been accredited. - Public registry of issued GHG permits available: A public registry of issued GHG permits is available on the e-GHG platform, and it is regularly updated with new issued permits. |
| Key issues in implementation | The issues in implementation were minimal, since the legislative and regulative framework were completed prior to the adopting of the Reform Agenda. The dominant risk in this step is not, whether the competent authority approves monitoring plans (it does), but whether public verifiability and downstream MRVA cycles (annual reporting and third‑party verification) become routine and transparent. Energy Community reporting confirms broad system establishment and that monitoring has begun for permit holders, but it also implies that full MRVA maturity depends on upcoming reporting/verification cycles. |
| Analyse how key principles of RGF were respected in the reform step implementation | Transparency Strong on legal texts and MoEP public announcements regarding training and first permit issuance. The list of accredited verifiers is available online, and the Accreditation Body of Serbia has conducted a transparent accreditation process, providing information to the broader public regularly. Public register of GHG emission permits exists in Serbia, listing operators covered by the system and the corresponding permit numbers. However, the permits themselves cannot be accessed or downloaded, as the register only provides basic administrative information. Although not strictly required by the current framework, public access to the permits, while protecting commercially sensitive data, would improve transparency and public oversight of the system. Inclusivity Since the legal and regulatory framework was completed prior to the adoption of Reform Agenda, the ability of CSO and broader public participation was limited. The rest of milestones were rather technical, so no broader participation was required. Operators and relevant institutions were included through MoEP‑organised trainings and workshops. Broader public/civil society participation is not structurally required for permit approvals, but publication of registry data is a key accessibility pathway for further enhancement of transparency and inclusivity. Proportionality for intended purpose The measures are proportionate to the intended purpose. Building MRVA capacity as a precondition for carbon pricing and eventual alignment with EU Emission Trading System (EU ETS). The framework applies to installations in scope defined by regulation and the Climate Change Law. No official evidence of selective exclusion from the legal obligation were found, though actual coverage of all eligible installations is an operational question beyond the step’s minimum requirement. |
| Public availability of evidence of implementation | Has the final source of verification (as per Reform Agenda) been made publicly available? If yes, please list the source (provide link) and date. Publicly available: Yes, although not as listed in the Reform Agenda. Source: - Government of the Republic of Serbia - E-GHG portal, including the registry of issued permits - Website of National Accreditation Body of Serbia Link: - https://e-ghg-portal.ekologija.gov.rs/ - https://www.ats.rs/sr/vesti/2025/09/ats-dodelio-prve-akreditacije-telima-za-verifikaciju-izvestaja-o-emisijama-ghg - https://zelena-agenda.euzatebe.rs/en/news/ghg-emissions-monitoring-training-for-thermal-power-plants-and-inspectorates - https://www.ekologija.gov.rs/saopstenja/vesti/izdata-prva-dozvola-za-emisije-gasova-sa-efektom-staklene-baste Date of publication: - Websites were accessed on February 26, 11:06. |
| Analyse quality of the final output of the reform step | Energy Community reporting concludes that Serbia has transposed core MRVA components (monitoring/reporting rulebook aligned with MMRR 2018/2066; verification/accreditation largely aligned with EU 2018/2067) and established a digital system supporting permitting and transparency. The European Commission similarly notes progress (“advanced”) on MRVA acquis in its Serbia Report. Taken together, the outputs are consistent with EU/Energy Community expectations for a candidate country preparing for carbon pricing/ETS, at least at the “MRVA readiness” stage. |

# Final assessment

| Assess formal achievement | Achieved |
| --- | --- |
| Elaboration of final assessment | The competent authority is demonstrably approving monitoring plans (through GHG permits) under a legal framework aligned to key MRVA acquis elements, supported by digitalization efforts and capacity building, meeting the Reform Agenda step’s intent and minimum requirement by December 2025. We therefore consider this reform step as achieved. |

https://zelena-agenda.euzatebe.rs/en/news/ghg-emissions-monitoring-training-for-thermal-power-plants-and-inspectorates (accessed on 26 February, 2026).

https://e-ghg-portal.ekologija.gov.rs/ (accessed on 26 February, 2026).

https://www.ats.rs/sr/vesti/2025/09/ats-dodelio-prve-akreditacije-telima-za-verifikaciju-izvestaja-o-emisijama-ghg (accessed on 26 February, 2026).

https://e-ghg-portal.ekologija.gov.rs/ (accessed on 26 February, 2026).