# Step overview

| Sub-area | 9.1. Democracy |
| --- | --- |
| Reform | 9.1.1. Prepare a Roadmap/Plan and address recommendations of OSCE/ODIHR and Council of Europe bodies on the electoral framework |
| Reporting indicator | Status of the electoral framework and its implementation |
| Reform Step | Second composite step due by December 2025. • Relevant legislation to address ODIHR and Council of Europe key recommendations, revised and adopted. Indicative list of laws subject to final approval of the WG include amendments to the following laws: Law on the Election of Members of Parliament, Law on Local Elections, Law on the Constitutional Court, Law on the Prevention of Corruption, and the Law on Financing Political Activities. • Improved capacities of Republic Electoral Commission and granting it its own secretariat. Achieving this step would mean Secretariat established by the decision of the National Assembly of the Republic of Serbia. |
| Step deadline | December 2025 |
| Step value in EUR | 27.175.246,75 |
| Responsible | Working group for the Improvement of the Electoral Process |
| Baseline | ODIHR February 2024 Report recommending to address as a matter of priority recommendations pertaining to REM, Voter Register and Working group |
| Sources of verification | Official Gazette (for the relevant legislation), Decision published |

# Analysis

| Define step milestones | - Identification by the Working Group of the ODIHR and Council of Europe key recommendations for the Improvement of the Electoral Process (hereinafter referred to as the “WG”) or another competent body. - Identification of laws that require revision or adoption to implement the key recommendations, in addition to those listed in the indicative list (Law on the Election of Members of Parliament, Law on Local Elections, Law on the Constitutional Court, Law on the Prevention of Corruption, and Law on Financing Political Activities), by the WG or another competent body. - Drafting of recommendations for practical measures to be implemented by the relevant authorities, where no legal amendment is required to fulfil the key recommendations of ODIHR/Council of Europe, by the WG or another newly established body. - Development of amendments through a consultative process involving stakeholders from the government, opposition, and civil society, within the WG or another (newly established) body. - Organisation of public debates and/or public hearings on draft laws (by competent ministries and/or parliamentary committees), with debates open for a minimum of 20 working days and published on the eConsultation Portal and other platforms (e.g., the WG page on the Parliamentary website), together with the final versions of draft laws. - Requesting the opinion of ODIHR (and, where appropriate, the Venice Commission) on the draft, by the WG or the public authority responsible for preparing the draft (e.g., ministry). - Properly addressing additional comments from ODIHR and the Council of Europe (Venice Commission), by the WG or another newly established body. - Adoption of laws or amendments by Parliament. - Promulgation and publication in the Official Gazette. |
| --- | --- |
| Analyse achievement of each milestone | For each identified milestone, provide a succinct analysis of its implementation process. Use numbered points corresponding to the defined milestones above. Please provide references wherever possible. For all milestones: The WG has been dysfunctional since February 2025, following the withdrawal of five members nominated by opposition parties and three members nominated by civil society organisations. There was no attempt to change the composition of the WG, to establish another body with similar tasks or to assign tasks of the WG to the competent ministries. - No effort was made to identify the ODIHR and Council of Europe key recommendations. According to the WG’s mandate, as defined in the decision on its establishment and subsequent revised decisions, its task was to prepare draft laws addressing all (not only “key”) ODIHR recommendations, stemming from various election observation missions, including the 2024 local elections. That mandate contained no reference to Council of Europe recommendations. - WG, within the scope of their work prepared (an informal) working paper, based on members’ inputs. The paper listed: a) all ODIHR recommendations (with the December 2023 election report as the most recent) that were not considered fully addressed; b) the identification of one or more laws that needed to be amended in order to address each recommendation; c) the identification of practical measures that could be undertaken by public authorities to implement the recommendations. - During its work, particularly in the first month (May 2024), WG members from civil society organisations prepared several recommendations for the competent authorities regarding practical measures to address certain deficiencies in the electoral process. For example, they proposed that the Public Prosecution Office should inform citizens about types of criminal offences related to elections and provide contact information for the relevant prosecution offices. Representatives of the ruling parties’ parliamentary groups within the WG were unwilling to vote on any of these proposals, either in favour or against. As a result, the WG lacked a quorum for decision-making.. - During its work in 2024, the WG did not reach the required two-thirds majority to propose any draft law. Such voting was organised only for two competitive proposals aimed at enabling an audit of the Voter Register. Individual WG members from civil society organisations and opposition parliamentary groups proposed amendments to several other laws, including the Law on the Prevention of Corruption, the Law on Financing of Political Activities, the Law on National and Local Elections, legislation on electronic media, and the Criminal Code. A representative of the ruling party (SNS) formally proposed amendments previously prepared and published in March 2024 by the Governmental Working Group for Cooperation with OSCE and ODIHR (listed in the “indicative list” of the reform steps), as well as amendments to the Law on Prevention of Corruption (partly reflecting the Transparency Serbia proposal). In 2025 and 2026 SNS representative in (former) WG proposed several new iterations of the amendments to the Law on United Voter Register. On 2 February 2026, the Secretary of Parliament shared with former WG members the draft amendments to the Law on Election of Members of Parliament, the Law on Local Elections, and the Law on the Constitutional Court, “prepared by the expert service of the Parliament”. Similarly, on 12 March 2026, he shared revised versions of these drafts, as well as draft amendments to the Law on Financing of Political Activities, “prepared by the Agency for Prevention of Corruption”. - No public debate was organised. The Parliamentary Committee for Constitutional Affairs and Legislature held several public hearings on various versions of amendments to the Law on the United Voter Register in 2025. - ODIHR provided its opinion on two laws (each with two versions) prepared within the WG: the Law on Prevention of Corruption and the Law on the United Voter Register. ODIHR also issued opinions, at the request of Parliament, on several subsequent iterations of the Law on the United Voter Register submitted to the Parliamentary Committee for Constitutional Affairs by SNS MP Ugljesa Mrdic. Finally, ODIHR provided opinions on three drafts upon Parliament’s request in February 2026. - ODIHR recommendations arising from its opinions on draft laws were only partially addressed in the Law on the United Voter Register, and the Parliament did not request an opinion on the final version. Recommendations relating to the Law on Prevention of Corruption were not addressed during the WG’s work in 2024. - No other law, apart from the amendments to the Law on the United Voter Register was amended. - See point 8. |
| Key issues in implementation | List and briefly explain key problems/issues arising in the reform step implementation. This can follow the milestone structure, but depending on the reform step, it can also be an analysis for the whole step. Please provide references wherever possible. The reform step itself is not sufficiently clearly defined. ODIHR reports, following the observation of each election, distinguish between “priority” and “other” recommendations.. On the other hand, the Council of Europe expert body, the Venice Commission, published a joint opinion for Serbia in 2022, in which seven recommendations were identified as “key” and labelled from A to G. The Working Group, responsible for implementing this reform step, was not functional during 2025 and 2026 and encountered numerous difficulties in its work, including polarization among stakeholders, lack of initiative, insufficient recognition of problems highlighted by ODIHR and the Venice Commission within ruling party coalitions, a complex decision-making process, and limited cooperation from other institutions. Legislative reform activities in 2025 and 2026 were largely undertaken by the Parliamentary Service, several MPs, or parliamentary committees, with subsequent attempts to link these activities to the (former) WG. It is further evident that the Parliamentary Expert Service is not authorised to prepare draft legislation. The primary factor obstructing the implementation of the reform step is the lack of trust that the Government or ruling coalition is genuinely committed to addressing key recommendations concerning the prevention of pressure on voters and the misuse of public resources, which are considered by other stakeholders in the country to be among the most critical issues¹. Beyond the absence of legislative initiatives, this lack of commitment is further evidenced by the recurrence or amplification of problematic practices previously highlighted by ODIHR during the local election campaigns of 2025 and 2026. |
| Analyse how key principles of RGF were respected in the reform step implementation | How transparent has the reform step implementation been? How has civil society and the wider public been informed about it? What data and information, including key documents, have been made publicly available? How inclusive was the implementation process? Has the implementation of the reform step allowed for participation of interested stakeholders, especially civil society organisations and – where applicable – business community? How was such participation ensured? What were the issues regarding their participation, if any? Depending on the reform step, provide an analysis of how other key RGF principles – apart from transparency and inclusivity analysed above – were respected in its implementation, as applicable: sound financial management, equal treatment, non-discrimination and proportionality for intended purpose. Please provide references wherever possible. Key issues Transparency Transparency of the WG’s work in 2024 was limited. Only brief reports, officially submitted proposals from members, and ODIHR opinions were available. Numerous negotiations concerning the provisions of certain laws—particularly amendments to the Law on the United Voter Register—also involved actors outside the WG. Regarding the drafts submitted in 2026, some crucial information is missing, most notably the legal basis for the Parliamentary Expert Service’s work on these drafts. Inclusivity The process was only partially inclusive. Some parliamentary groups chose not to participate in the WG in 2024. Regarding civil society organisations, three were formally invited to take part in the WG, while other CSOs and citizens had very limited opportunities to influence the process, for example by speaking at public hearings on the Law on the United Voter Register. Their comments and suggestions were not systematically addressed. |
| Public availability of evidence of implementation | Has the final source of verification (as per Reform Agenda) been made publicly available? If yes, please list the source (provide link) and date. Not applicable. |
| Analyse quality of the final output of the reform step | To what extent does the final output of this reform step respect the applicable EU membership requirements/principles/standards? Not applicable. |

# Final assessment

| Assess formal achievement | Not achieved. |
| --- | --- |
| Elaboration of final assessment | A clear list of “key recommendations” has not been established, making it impossible to verify progress based on factual evidence. The WG has not been functional for more than a year, and no attempt was made to establish an alternative multi-stakeholder consultative mechanism. During its work in 2024, the WG failed to achieve the required majority for any proposal. The adopted amendments to the Law on the Unified Voter Register do not fully reflect ODIHR’s opinions on previous drafts. Some legislative reforms were initiated in 2026, but they were neither prepared within the WG nor through any other legally recognised procedure. |

Available here: https://www.parlament.gov.rs/narodna-skupstina-/sastav/radna-tela/radne-grupe.4457.html

The list of laws is available in the Report of WG chairperson covering May / October 2024 period: https://www.parlament.gov.rs/upload/documents/dokumenta/Informacija%20o%20radu%20Radne%20grupe%20za%20unapredjenje%20izbornog%20procesa%20u%20periodu%20od%2031.%20maja%20do%202.%20oktobra%202024.%20godine.pdf

See more in the first report of the WG chair, available here: https://www.parlament.gov.rs/upload/documents/dokumenta/Informacija%20predsedavajuceg%20o%20radu%20Radne%20grupe%2021.05.2024.pdf

See more in the report of WG chair, covering period from October 2024 till January 2025, available here: https://www.parlament.gov.rs/upload/documents/dokumenta/Informacija%20o%20radu%20Radne%20grupe%20za%20unapredjenje%20izbornog%20procesa%20u%20periodu%20od%2011.%20oktobra%20do%2031.%20januara%202025.%20godine.pdf

Proposals are listed here: https://www.parlament.gov.rs/upload/documents/dokumenta/Informacija%20o%20radu%20Radne%20grupe%20za%20unapredjenje%20izbornog%20procesa%20u%20periodu%20od%2031.%20maja%20do%202.%20oktobra%202024.%20godine.pdf and their texts are available here: https://www.parlament.gov.rs/narodna-skupstina-/sastav/radna-tela.5001.html

Proposals are available here: https://www.parlament.gov.rs/narodna-skupstina-/sastav/radna-tela.5033.html

Documents not published by the Parliament.

https://www.parlament.gov.rs/Na_Devetom_javnom_slu%C5%A1anju_predstavljen_nacrt_zakona_o_izmenama_i_dopunama_Zakona_o_jedinstvenom_bira%C4%8Dkom_spisku.51543.941.html

ODIHR oppinions are available here: https://www.parlament.gov.rs/narodna-skupstina-/sastav/radna-tela.5033.html

https://odihr.osce.org/odihr/662623

http://www.parlament.gov.rs/upload/archive/files/lat/pdf/predlozi_zakona/14_saziv/2147-25%20-%20Lat..pdf

https://www.osce.org/odihr/elections/serbia

Strasbourg, 19 December 2022, Opinion No. 1071/2021 OSCE/ODIHR Opinion-No. ELE-SRB/449/2022 CDL-AD(2022)046 Or. Engl. EUROPEAN COMMISSION FOR DEMOCRACY THROUGH LAW (VENICE COMMISSION) OSCE OFFICE FOR DEMOCRATIC INSTITUTIONS AND HUMAN RIGHTS (OSCE/ODIHR) SERBIA

“JOINT OPINION ON THE CONSTITUTIONAL AND LEGAL FRAMEWORK GOVERNING THE FUNCTIONING OF DEMOCRATIC INSTITUTIONS  ELECTORAL LAW AND ELECTORAL ADMINISTRATION”, page 6, available at:

https://odihr.osce.org/sites/default/files/f/documents/7/e/535266.pdf

Partial achievement possible only for quantitative steps. For such steps, insert level (percentage) of implementation, if available.