# Step overview

| Sub-area | 9.1. Democracy |
| --- | --- |
| Reform | 9.1.1. Prepare a Roadmap/Plan and address recommendations of OSCE/ODIHR and Council of Europe bodies on the electoral framework |
| Reporting indicator | Status of the electoral framework and its implementation |
| Reform Step | First composite step due by December 2024 (subject to ODIHR assessment as the verification mechanism), • WG composed in accordance with the ODIHR recommendation. The would mean inter-agency Working Group on Co-ordination and Follow-up of the Implementation of Recommendations for the Improvement of the Electoral Process should act in full transparency, with the inclusion of relevant stakeholders, such as civil society organizations. • A meaningful audit of voter register completed in accordance with ODIHR recommendations. This step means establishment of the Commission which will oversee and control voters register. The Commission should include representatives of opposition, as well as relevant civil society organizations. The implementation of this recommendation should be recognized/verified by ODIHR. • REM Council is re-elected (in line with the Law on electronic media) in a transparent and inclusive process. Clear explanation of this step is given in the relevant law. |
| Step deadline | December 2024 |
| Step value in EUR | 20.381.435,06 |
| Responsible | Working group for the Improvement of the Electoral Process |
| Baseline | ODIHR February 2024 Report recommending to address as a matter of priority recommendations pertaining to REM, Voter Register and Working group |
| Sources of verification | ODIHR Report, Official Gazette, Decision on the establishment of the Working Group for the Improvement of the Electoral Process published |

# Analysis

| Define step milestones | For each step, based on the provisions of the Reform Agenda, define several key milestones for full achievement and number them. E.g. for a legislative step, that can include: 1. Announcement of the work on the new law, 2. Setting up a working group, 3. Initial consultation (via eConsultation portal), 4. Publication of all key materials on eConsultation portal (draft law, RIA, consultation report), 5. Public debate in accordance with the Rules of Procedure of the Government, 6. Adoption in Parliament (with analysis of the adoption procedure). Depending on the reform step, make sure that milestones take into account applicable legal requirements (e.g. Law on the Planning System, Government Rules of Procedure, etc.). - Drafting phase of the Law on the Unified Voter Register and work of the Working Group successfully finalised, in accordance with the Decision on Establishment (at least 2/3 of members’ votes for one proposal) - Consultation process and public hearings organised in accordance with established procedure - Parliamentary phase and political alignment ensured consensus of key stakeholders on legislative changes - ODIHR assessment of final draft is positive - Amendments to the Law on the Unified Voter Register are adopted in the Parliament - Promulgation and entry into force of the law on the Unified Voter Register - Appointment and constitution of the Commission for Audit - Adoption of internal framework and Methodology on time - Implementation phase: audit of the voter register conducted in accordance with the amended Law and Methodology - Compliance of administrative authorities with Commissions’ requests ensured - Final reporting produced and parliamentary oversight conducted in a timely manner |
| --- | --- |
| Analyse achievement of each milestone | For each identified milestone, provide a succinct analysis of its implementation process. Use numbered points corresponding to the defined milestones above. Please provide references wherever possible. ## 1. Drafting phase of the Law on the Unified Voter Register and work of the Working Group (2025) The reform of the Law on the Unified Voter Register (UVR) was initiated in early 2024 as part of Serbia’s commitments under electoral reform and rule of law frameworks (Chapter 23). Although the mandate of the Working Group for Improvement of Electoral Procedure (WG), composed of MPs from the ruling majority and opposition, as well as three CSO representatives, was to foster the implementation of all ODIHR recommendations, the expected length of the process led the WG to initially focus on launching an audit of the Unified Voter Register (UVR). This initiative was thereafter accepted by both domestic and international stakeholders as a priority and, alongside the election of members of the REM Council, became the only ODIHR-related reform to be actively pursued, even after WG effectively stopped working (December 2024). The WG discussed and decided on two competitive draft versions of the Law on the UVR on its December 2024 session. Neither consensus not qualified majority (2/3 of votes) could not be reached for any of proposals: one prepared by the CSO CRTA, and another by ruling majority MP Uglješa Mrdić. Both drafts were submitted to the relevant parliamentary committee—the Committee on Constitutional and Legal Affairs—for consideration. However, the Committee, dominated by MPs from the ruling majority, decided to include into agenda of public hearings another iteration of the draft proposed by SNS (not the one that was discussed within the WG), while falsely presented it as a part of previous process. That was one of the reasons for CSO representatives to withdraw from the WG. The opposition MP groups’ representatives withdraw even earlier, being dissatisfied with the process and lack of willingness of ruling parties’ representatives to support CRTA’s draft, which they considered “necessary minimum”. The situation was later (during the 2025) pushed forward out of the scope of WG, with involvement of international stakeholders, resulting in a final draft that was accepted by the majority of WG members. After an extensive harmonization where ruling parties representatives submitted as many as 12 versions of draft, several of which were presented at nine public hearings in Parliament, while five were submitted to ODIHR for an official opinion. ODIHR provided preliminary comment to other versions of that draft, including on two CRTA’s and two SNS versions, that were produced during 2024, while WG was still in place. On 28 March 2025, ODIHR issued its first official Opinion, confirming that the Serbian authorities had developed a structured draft and formally entered the legislative phase, thereby marking the beginning of systematic alignment with international electoral standards. Subsequent ODIHR opinions were issued on 4 June 2025, 10 July 2025, 3 September 2025, and 3 October 2025; however, the final draft (adopted by the Parliament) was not submitted to ODIHR for review. ## 2. Consultation process and public hearings (2025) The various versions of the draft law underwent several rounds of consultations between January and July 2025 - nine public hearings organized within the Parliament. Four of the public hearings featured draft laws presented as the outcome of the Working Group’s work, despite the fact that even on first such hearing (January 27th 2025), Committee included on Agenda (third) version of SNS draft, that was not part of WG discussions. Subsequently, CSO representatives from WG did not attend further public hearings, while some of opposition representatives did it occasionally. ODIHR issued a series of follow-up opinions between March and October 2025, acknowledging iterative improvements to the drafts while noting that several recommendations remained unaddressed. ## 3. Parliamentary phase and political alignment (mid–late 2025) Following extensive back-and-forth versions, the draft entered parliamentary procedure on 2 November 2025 and was subsequently adopted under an urgent procedure on 7 November 2025. While the final version included some improvements, that were welcomed by opposition parties and CSOs, as well as ODIHR, there was no full consensus among stakeholders. Several opposition parties unsuccessfully tried to influence content of the Law through amendments during the parliamentary procedure. Transparency Serbia published the list of unresolved issues and legal loopholes in the bill. While there was no consensus on the content, following developments showed that the Law was “good enough” for two qualified CSOs that decided to take part in the further audit procedure (CRTA and CESID), as well as for some of opposition MP groups. ## 4. ODIHR assessment of compliance (2024 and 2025) ODIHR noted that the Serbian authorities had undertaken an extensive harmonization process involving representatives of the authorities, opposition, and CSOs within the Working Group on the improvement of the electoral process. ODIHR provided unofficial comments to other versions of that draft, including on two CRTA’s and two SNS versions, that were produced during 2024, while WG was still in place. Over this period, as many as 12 draft versions were prepared, several of which were presented at nine public hearings in Parliament, while five were submitted to ODIHR for an official opinion. On 28 March 2025, ODIHR issued its first official Opinion, confirming that a structured draft had been developed and that the legislative process had formally begun, signalling initial steps toward alignment with international electoral standards. Subsequent Opinions, issued on 4 June, 10 July, 3 September, and 3 October 2025, acknowledged iterative improvements. However, the final draft was not submitted for review, leaving some recommendations unaddressed. Overall, ODIHR’s assessment indicates that while progress toward compliance was evident, full alignment with international standards was not yet achieved at that stage. ## 5. Adoption of the law on the Unified Voter Register (Q4 2025) The Law on Amendments to the Law on the Unified Voter Register was adopted by the National Assembly of the Republic of Serbia on 7 November 2025, under an urgent procedure, just five days after entering parliamentary procedure on 2 November 2025, thereby concluding the legislative phase of the reform. ## 6. Promulgation and entry into force of the law on the Unified Voter Register (late 2025) Following its adoption, the Law was promulgated and published in the Official Gazette of the Republic of Serbia. It entered into force within the timeframe specified in its final provisions, generally eight days after publication, while certain provisions include specific deadlines. The law thus triggered obligations related to institutional setup and implementation. ## 7. Appointment and constitution of the Commission (late 2025) In accordance with the Law, the National Assembly initiated the procedure for appointing members of the audit commission, by issuing a public call for candidates on 17 November 2025. A public call for nominations was issued within the legally prescribed deadline (45 days after entry into force), outlining eligibility criteria and procedural requirements. Parliamentary committee violated procedure by providing “second chance” to one opposition MP group to propose candidates, even if that MP group previously rejected such opportunity, and another MP groups (with smaller number of MPs) was invited to propose candidates in the meantime. On 29 December 2025, the Committee determined the list of candidates and submitted it to the National Assembly for election. On 28 January 2026, the National Assembly elected members of the Commission for the audit of UVR. Members of the Commission were appointed within the legal deadline following a selection procedure conducted by the competent parliamentary Committee. The Commission was formally constituted shortly thereafter and held its constitutive session, electing its leadership and commencing operations. First sitting of the Commission took place on 4 February 2026. ## 8. Adoption of internal framework and methodology (Q1 2026) After its establishment, the Commission adopted its internal rules of procedure on the continuation of its first sitting on 13 February 2026. Work plan and financial plan were adopted on the sitting on 3 March 2026. The next two sittings were dedicated to adoption of additional internal regulation and establishing different working groups within the Commission. The fourth sitting, which commenced on 27 March 2026, initiated the procedure for adopting the regulation on the methodology for auditing the Unified Voter Register (UVR). This document was adopted on the sitting on 3 April 2026. ## 9. Implementation phase: audit of the voter register (2026 – ongoing) The Commission has initiated the audit process in 2026, in line with the legal requirement to complete the review within a defined timeframe (up to 9 months). The audit includes cross-checking administrative databases, identifying inconsistencies, and assessing systemic weaknesses in the voter register. ## 10. Compliance of administrative authorities (2026 – ongoing) The effectiveness of the reform depends on whether public administration bodies act upon the commission’s findings. ODIHR has previously emphasized this as a critical issue, noting that the legal framework must ensure enforceability and follow-up. Early indications suggest that compliance remains uneven. Opposition representatives, primarily members of the Commission for the revision of the voter register from the Party of Freedom and Justice/Stranka slobode i pravde (SSP), including Marko Dimić and Ana Gođevac, complain that the authorities are systematically obstructing their work and restricting access to key data, making effective oversight nearly impossible. Although the law guarantees full access to the voter register through a dedicated web module, they stress that this access is limited only to the room where the Commission sessions are held, which further constrains their ability to conduct thorough analysis. At the same time, they report serious irregularities in the voter register, such as missing essential data (e.g. voters without a recorded place of birth), inconsistencies in how entries are recorded (sometimes only at the municipality level), and unexplained patterns of address changes, all of which, combined with manual and non-transparent updating practices, create significant risks of manipulation and political misuse. SSP additionally accuses the Ministry of Public Administration of deliberately undermining the Commission’s work, including by withholding information and enabling discretionary control over when and how voter data is updated. ## 12. Final reporting and parliamentary oversight (expected late 2026 onward) Upon completion of the audit, the Commission is expected to submit a final report with findings and recommendations to the National Assembly. The Assembly will then review the report, adopt conclusions, and monitor implementation through its oversight function. This phase will determine the overall effectiveness and sustainability of the reform. |
| Key issues in implementation | List and briefly explain key problems/issues arising in the reform step implementation. This can follow the milestone structure, but depending on the reform step, it can also be an analysis for the whole step. Please provide references wherever possible. The drafting phase of the reform raised concerns among civil society organizations and relevant stakeholders regarding the level of inclusiveness and transparency of the process. Although formal mechanisms for participation were established, the process did not result in broad consensus among political and societal actors. The functioning of the parliamentary Working Group, including the withdrawal of some participants, pointed to limitations in achieving an inclusive and trust-building reform environment. This has affected the perceived legitimacy of the reform from its early stages. The main limiting factor for the successful work of the process was the approach taken from the outset by representatives of the authorities, both in Parliament and in the ministries, namely that problems with the voter register either did not exist or were of minor importance, despite ODIHR recommendations and findings by domestic actors from the opposition and civil society. This significantly slowed down work on legislative amendments, both within the Working Group and after it ceased functioning. In addition, although ODIHR recommendations were clear, the authorities accepted them only incrementally. Disputes over the composition of the Commission and its decision-making procedures led to the neglect of other important issues, particularly regarding the Commission’s powers vis-à-vis state administration bodies. These issues were only addressed (to certain extent) at a later stage, following consultations conducted by ODIHR with stakeholders from various sectors. Following the adoption of the Law, stakeholders have raised questions regarding the extent to which the reform will lead to substantive improvements in electoral integrity. While the establishment of new mechanisms, such as the audit commission, represents a formal step forward, concerns remain as to whether these measures will effectively address long-standing structural challenges related to the accuracy and reliability of the voter register. Assessments by ODIHR have been frequently referenced by stakeholders, highlighting that the reform only partially aligns with international standards. In its opinions, ODIHR noted that several key recommendations were not fully incorporated, particularly those concerning the independence of the audit mechanism, transparency of the process, and safeguards against undue influence. These gaps continue to be central to ongoing discussions about the effectiveness of the reform. The independence of the newly established audit commission has emerged as a key issue in stakeholder discussions. Concerns have been raised regarding the appointment procedure and whether it provides sufficient safeguards to ensure impartiality and credibility. These concerns are consistent with ODIHR’s observations emphasizing the importance of strong institutional guarantees for independent oversight bodies. Transparency of the audit process remains another important area of concern. Civil society organizations and experts have pointed to the need for clear and publicly accessible methodologies, as well as adequate access to relevant data. Ensuring transparency is seen as essential for building public trust and enabling independent verification of audit findings. These concerns are further shaped by broader issues identified in previous electoral cycles, including questions about the accuracy of voter lists and the effectiveness of verification mechanisms. Such experiences continue to influence stakeholder perceptions and underline the importance of ensuring that the current reform delivers measurable improvements in practice. The implementation phase presents additional challenges. Stakeholders have emphasized that the effectiveness of the reform will depend not only on the work of the Commission, but also on the responsiveness of public administration bodies to its findings and recommendations. Finally, stakeholders underline that the reform of the Unified Voter Register should be considered within the broader electoral framework. Issues such as media environment, voter pressure, and the use of public resources continue to affect electoral integrity. In this context, the impact of the reform will depend on parallel progress in these areas. |
| Analyse how key principles of RGF were respected in the reform step implementation | How transparent has the reform step implementation been? How has civil society and the wider public been informed about it? What data and information, including key documents, have been made publicly available? How inclusive was the implementation process? Has the implementation of the reform step allowed for participation of interested stakeholders, especially civil society organisations and – where applicable – business community? How was such participation ensured? What were the issues regarding their participation, if any? Depending on the reform step, provide an analysis of how other key RGF principles – apart from transparency and inclusivity analysed above – were respected in its implementation, as applicable: sound financial management, equal treatment, non-discrimination and proportionality for intended purpose. Please provide references wherever possible. ### Transparency The reform of the Unified Voter Register (UVR) included formal measures aimed at ensuring transparency, such as publication of the draft law, official parliamentary records, and ODIHR opinions. Key documents, including the draft law, amendments, and explanatory notes, were made publicly accessible through the National Assembly portal. ODIHR assessments and some of the civil society commentaries were also available online. However, comprehensive overview of proposals from the public hearing and follow-up actions based on such comments and proposals was not produced. Civil society organizations (CSOs) and media outlets reported on the draft law, its adoption, and the establishment of the audit commission, indicating a baseline level of public information. However, several stakeholders noted that while documents were available, the dissemination of information to the wider public was limited, with little effort to provide explanatory summaries, timelines, or accessible analysis of the implications for voters. This limited the ability of non-specialist audiences to track the process in real time. ### Inclusivity The implementation process incorporated formal opportunities for participation, such as parliamentary public hearings. Despite these mechanisms, inclusivity in practice was partial. Stakeholders reported that participation was limited by procedural constraints, tight deadlines, and the dominance of ruling-majority actors in shaping both the draft and the appointment of commission members. Opposition parties and some CSOs withdrew from working groups at various points, citing procedural violations. While the process allowed participation, it did not always ensure equal weight to the input of independent stakeholders, limiting its overall inclusivity. Furthermore, since there was not public debate (as it would be if the law was prepared by the ministry), there is no list of recommendations submitted during the consultation process, neither list of reasoning for their acceptance or rejection. ### Other Key RGF Principles Sound financial management: The implementation did not raise specific budgetary concerns, as the establishment of the audit commission and the conduct of the audit were carried out using existing parliamentary and administrative resources. There were no publicly reported deviations from planned resource allocation. Equal treatment and non-discrimination: The Law and its implementing procedures applied uniformly to all voters in the registry. Stakeholders noted that, in principle, safeguards were intended to prevent discriminatory practices in reviewing the voter register. However, questions remain regarding whether the mechanisms provide equal influence for all civil society actors and political parties in oversight activities. Proportionality for intended purpose: The reform measures, including the creation of an independent commission with a clear methodology for auditing the voter register, appear proportional to the stated objective of improving the accuracy, transparency, and credibility of the registry. Nevertheless, stakeholder feedback suggests that proportionality in practice is partly undermined by limited public accessibility of data and procedural constraints affecting participation. |
| Public availability of evidence of implementation | Has the final source of verification (as per Reform Agenda) been made publicly available? If yes, please list the source (provide link) and date. While the regulatory framework and Commission for monitoring and oversight of the voter register have been established, the thorough revision of the voter register in line with ODIHR recommendations has yet to be completed and made publicly available. Consequently, there is no finalized source of verification to provide the implementation of this step. |
| Analyse quality of the final output of the reform step | To what extent does the final output of this reform step respect the applicable EU membership requirements/principles/standards? The final output of the Unified Voter Register reform partially aligns with EU membership requirements and standards. Legally, the Law establishes the audit commission, defines a methodology for reviewing the voter register, and provides formal opportunities for civil society engagement, which correspond to EU expectations for institutional frameworks and electoral oversight. In practice, however, transparency, inclusivity, and the independence of the commission are not fully realized as procedural constraints, limited public outreach reduce the effectiveness of stakeholder participation. To fully meet EU standards, continued monitoring, proactive engagement of civil society, and consistent implementation of audit findings are necessary to ensure that the reform achieves tangible improvements in electoral integrity and public trust. |

# Final assessment

| Assess formal achievement | Not achieved |
| --- | --- |
| Elaboration of final assessment | This step is considered not achieved. Although the regulatory framework has been adopted and the Commission for Monitoring and Oversight of the Voter Register has been established, the results of its work in practice have yet to be seen. Full implementation, including a thorough revision of the voter register as recommended by ODIHR, remains to be carried out and confirmed by ODIHR. |