# Reform step monitoring template

# Step overview

| Sub-area | 9.3. Fight against organized crime |
| --- | --- |
| Reform | 9.3.1. Tackling of organized and serious crime |
| Reporting indicator | Status of organised and serious crime related legislation and its implementation |
| Reform Step | - Following consultations with the Commission, new strategic document and accompanying Action Plan *(2025-2030) for the control of Small arms and light weapons (SALW) in line with the provisions of the revised Regional SALW Roadmap for Western Balkans are adopted |
| Step deadline | June 2025 |
| Step value in EUR | 6.793.811,69 |
| Responsible | Ministry of Interior |
| Baseline | Republic of Serbia strategic framework in the area of SALW is in place. Revised SALW Regional Roadmap is to be adopted by June 2025. |
| Sources of verification | Official website of the Ministry of the Interior, where the documents will be made public, after adoption. Previously, during the process prior to adoption, the documents will be published – eConsultations portal. |

# Analysis

| Define step milestones | For each step, based on the provisions of the Reform Agenda, define several key milestones for full achievement and number them. E.g. for a legislative step, that can include: 1. Announcement of the work on the new law, 2. Setting up a working group, 3. Initial consultation (via eConsultation portal), 4. Publication of all key materials on eConsultation portal (draft law, RIA, consultation report), 5. Public debate in accordance with the Rules of Procedure of the Government, 6. Adoption in Parliament (with analysis of the adoption procedure). Depending on the reform step, make sure that milestones take into account applicable legal requirements (e.g. Law on the Planning System, Government Rules of Procedure, etc.). - Setting up the working group in an open process, open to civil society organisations - The working group jointly formulates the proposed amendments through the participation and consensus of all its members - Publication of the draft document on eConsultation Portal - Consultation performed on the Portal - Public debate conducted with minimum duration of 20 days - Consultation and public debate report(s) published on eConsultation Portal, along with final version of the program with action plan - Adoption at the Government session - Publication in the Official Gazette and the website of the Ministry of the Interior/Government |
| --- | --- |
| Analyse achievement of each milestone | For each identified milestone, provide a succinct analysis of its implementation process. Use numbered points corresponding to the defined milestones above. Please provide references wherever possible. - The composition of the Working Group has not been published. Following a public call (16–28 October 2024) issued by the Ministry for Human and Minority Rights and Social Dialogue, in cooperation with the Ministry of the Interior (MoI), for civil society representatives to join the Working Group, the procedure was discontinued due to a lack of applications. - There is no publicly available information on the discussions held within the Working Group. - The draft Program for the Control of Small Arms and Light Weapons, Ammunition and Explosives in the Republic of Serbia for the period 2025–2030, along with the accompanying Action Plan for 2025–2027 (hereinafter: the Program and Action Plan), was published on the e-Consultation Portal on 23 May 2025. - Consultations were conducted via the Portal from 23 to 30 May 2025 through written submissions. No submissions were received. - A public debate was conducted via written submissions on the e-Consultations Portal from 29 August to 19 September 2025. No submissions were received during this period. - Reports on the consultation and public debate were published on the e-Consultation Portal on 3 June 2025 and 2 October 2025, respectively, together with the final version of the Program and Action Plan. - The Program for the Control of Small Arms and Light Weapons, Ammunition and Explosives in the Republic of Serbia for the period 2025–2030, along with the accompanying Action Plan for 2025–2027, was adopted at a Government session on 26 December 2025. - The documents were published in the Official Gazette (No. 119/2025) on 29 December 2025 and on the website of the Ministry of the Interior. |
| Key issues in implementation | List and briefly explain key problems/issues arising in the reform step implementation. This can follow the milestone structure, but depending on the reform step, it can also be an analysis for the whole step. Please provide references wherever possible. Although this issue was in the public spotlight in 2023 following the mass shootings in May of that year, it is notable that the drafting of these documents went largely unnoticed. While the Ministry of the Interior formally complied with the required procedural steps, it did not actively promote the process. As a result, no applications were submitted for participation in the Working Group, and no comments were received during the consultation or public debate phases. Several relevant civil society organizations (CSOs) reported that they had not received the invitation by email. The consultation period lasted only seven days, and the public debate coincided with the public debate on a set of three key criminal law drafts (the Criminal Code, the Criminal Procedure Code, and the Law on Juvenile Justice), which drew significant public attention. Due to this overlap, the Autonomous Women’s Center was able to submit its comments only one day after the public debate had formally closed. According to the Ministry, these comments were nevertheless reviewed and, as they concerned amendments to the legislative framework in the relevant area, were forwarded to the competent authorities responsible for legislative changes. However, this information is not reflected in the official report on the conducted public debate. |
| Analyse how key principles of RGF were respected in the reform step implementation | How transparent has the reform step implementation been? How has civil society and the wider public been informed about it? What data and information, including key documents, have been made publicly available? How inclusive was the implementation process? Has the implementation of the reform step allowed for participation of interested stakeholders, especially civil society organisations and – where applicable – business community? How was such participation ensured? What were the issues regarding their participation, if any? Depending on the reform step, provide an analysis of how other key RGF principles – apart from transparency and inclusivity analysed above – were respected in its implementation, as applicable: sound financial management, equal treatment, non-discrimination and proportionality for intended purpose. Please provide references wherever possible. Transparency and inclusivity The process formally complied with procedural requirements but demonstrated limited transparency and inclusiveness in practice. Although draft documents, consultation periods, reports, and the final adopted Program and Action Plan were published on the e-Consultations Portal and later in the Official Gazette, the composition of the Working Group was not made public. A call for civil society participation in the Working Group was published on the e-Consultations Portal but resulted in no applications. The consultation period lasted only seven days, while the public debate lasted 20 days, in line with the minimum legal requirement. Both processes were conducted exclusively through written submissions, and no comments were received Overall, despite the sensitivity of the issue following the mass shootings in 2023, the process remained low-profile. |
| Public availability of evidence of implementation | Has the final source of verification (as per Reform Agenda) been made publicly available? If yes, please list the source (provide link) and date. Publicly available: YES Official Gazette: adopted Program with Action Plan, available at https://pravno-informacioni-sistem.rs/eli/rep/sgrs/vlada/drugiakt/2025/119/1 Government website: https://www.srbija.gov.rs/prikaz/939847 MoI website: - Program for the Control of Small Arms and Light Weapons, Ammunition and Explosives in the Republic of Serbia for the Period 2025–2030, with the Action Plan for 2025–2027 - Conclusion of the Committee on the Legal System and State Bodies and the Public Debate Program - Invitation to Participate in the Public Debate - Form for Submitting Proposals and Suggestions - Report on the Conducted Public Debate Available at: https://www.mup.gov.rs/wps/portal/sr/dokumenti/Strategije (last accessed 26/02/2026) e-Consultations portal: - draft documents for consultations - draft documents for public debate - announcement and program of the public debate - Form for Submitting Proposals and Suggestions - Report on the Conducted Public Debate available at: https://ekonsultacije.gov.rs/topicOfDiscussionPage/465/4 |
| Analyse quality of the final output of the reform step | To what extent does the final output of this reform step respect the applicable EU membership requirements/principles/standards? Serbia’s Program for the Control of Small Arms and Light Weapons, Ammunition and Explosives 2025–2030, together with the Action Plan 2025–2027, represents a significant step toward operationalizing the Western Balkans SALW Control Roadmap 2025–2030. The Program is structured around strategic goals, measurable indicators, and a formal reporting cycle, aligning with the Roadmap’s emphasis on a harmonized legislative framework, risk reduction, and institutional coordination. It establishes a six-year strategic framework, accompanied by a three-year action plan and annual reporting obligations, thereby meeting key regional expectations for national arms control frameworks and monitoring mechanisms. Serbia’s integration of secondary legislation, along with training for prosecutors, judges, and enforcement personnel, further strengthens alignment with the EU acquis and relevant international standards. From an operational perspective, the Program demonstrates substantial incorporation of key Roadmap elements, including improved record-keeping, marking and deactivation systems, enhanced oversight of explosives storage, and capacity-building initiatives for law enforcement and judicial actors. These components reflect sustained efforts to support evidence-based policy implementation and strengthen cross-institutional cooperation, in line with the Roadmap’s comprehensive approach to SALW control. The inclusion of performance indicators and quantifiable targets—particularly in the areas of deactivation and regulatory compliance—marks important progress toward achieving measurable outcomes. Notwithstanding these strengths, civil society stakeholders—most notably the Autonomous Women’s Center (AWC)—have identified gaps in the Program’s approach to specific preventive and harm-reduction measures. In its commentary on the draft, AWC pointed to omissions related to stricter acquisition criteria for certain categories of civilian firearms, the introduction of household notification requirements for applicants, enhanced health capacity checks, and the regulation of replica weapons and military-style training involving such replicas. It also highlighted the need for stronger protections for minors in hunting and shooting contexts. In addition, concerns were raised regarding persistent shortcomings in secure storage practices and accountability mechanisms for surrendered weapons. These concerns were underscored by reported incidents of lost inventory following voluntary weapons surrender campaigns. In terms of societal impact and alignment with broader Roadmap goals—such as gender-responsive policymaking and the prevention of misuse—the Program could more explicitly integrate measures addressing gender-based violence involving firearms, as well as community-oriented awareness campaigns. While structural and enforcement mechanisms are well represented, feedback from civil society highlights opportunities to strengthen the focus on preventive strategies, health and safety checks, and protections for vulnerable populations. Enhancing these aspects would improve Serbia’s alignment with the Roadmap’s comprehensive vision, including its links to the Sustainable Development Goals on peace, justice, and gender equality. |

# Final assessment

| Assess formal achievement | Achieved |
| --- | --- |
| Elaboration of final assessment | Provide a brief and to-the-point elaboration of your final assessment. Procedurally, the drafting process followed the required public consultation procedures, although it remained largely low-profile. Substantively, the Program and Action Plan demonstrate alignment with the objectives of the Western Balkans SALW Roadmap. However, further strengthening of gender-responsive safeguards, preventive measures, and accountability mechanisms would enhance full alignment with evolving EU and regional best practices. We therefore assess this reform step as achieved. |

The decision on the establishment of the Working Group was not published on the e-Consultations Portal. However, the adopted Program states that the Working Group consisted of representatives of the Ministry of Interior, the Ministry of Justice, the Ministry of Foreign Affairs, the Ministry of Internal and External Trade, the Ministry of Finance – Customs Administration, the Ministry of Health, the Supreme Public Prosecutor’s Office, and the Agency for Testing, Stamping and Marking of Firearms, Devices and Ammunition, as well one representative of the National Firearms Association of Serbia.