# Reform step monitoring template

# Step overview

| Sub-area | 9.3. Fight against organized crime |
| --- | --- |
| Reform | 9.3.1. Tackling of organized and serious crime |
| Reporting indicator | Status of organised and serious crime related legislation and its implementation |
| Reform Step | - The Law on internal affairs addressing the issue of police autonomy from the Ministry of Interior during pre-investigation and investigation phases and recommendations from the Committee for Prevention of Torture is adopted |
| Step deadline | June 2025 |
| Step value in EUR | 20.381.435,06 |
| Responsible | Ministry of Interior |
| Baseline | Adoption of the new Law on Internal Affairs states that one of the tasks of the Ministry of the Interior is to provide conditions for the prevention of torture and degrading procedures and the control of police actions towards persons deprived of their liberty, with the implementation of the CPT recommendations. Also, the Law will ensure that the police have operational autonomy from the Ministry. |
| Sources of verification | Official Gazette of Republic of Serbia |

# Analysis

| Define step milestones | For each step, based on the provisions of the Reform Agenda, define several key milestones for full achievement and number them. E.g. for a legislative step, that can include: 1. Announcement of the work on the new law, 2. Setting up a working group, 3. Initial consultation (via eConsultation portal), 4. Publication of all key materials on eConsultation portal (draft law, RIA, consultation report), 5. Public debate in accordance with the Rules of Procedure of the Government, 6. Adoption in Parliament (with analysis of the adoption procedure). Depending on the reform step, make sure that milestones take into account applicable legal requirements (e.g. Law on the Planning System, Government Rules of Procedure, etc.). - Setting up the working group in an open and transparent process - The working group jointly formulates the draft law through the participation and consensus of all its members - Publication of the draft on eConsultation Portal - Public debate conducted with minimum duration of 20 working days - Consultation and public debate report(s) published on eConsultation Portal, along with final draft version - Bill adopted at the Government session and submitted to Parliament - Parliamentary debate (in relevant committees and plenum) - Adoption in the Parliament - Publication in the Official Gazette |
| --- | --- |
| Analyse achievement of each milestone | For each identified milestone, provide a succinct analysis of its implementation process. Use numbered points corresponding to the defined milestones above. Please provide references wherever possible. - The Working Group (WG) was established on November 6, 2024. On November 14, a notice was published on the e-Consultations portal announcing the start of work on drafting the law and the decisions on the establishment of the WG for that purpose. The WG consists exclusively of representatives from various units of the Ministry of the Interior and the Police Directorate, as well as representatives of three police unions. - The work of the Working Group was not open to the public. - The Draft Law has still not been finalized or published. - / - / - / - / - / - / |
| Key issues in implementation | List and briefly explain key problems/issues arising in the reform step implementation. This can follow the milestone structure, but depending on the reform step, it can also be an analysis for the whole step. Please provide references wherever possible. Given that this is the third version of the Draft Law on Internal Affairs, it is unclear whether the work of the Working Group started from scratch or continued from the previous version, which had required substantial revisions. The two previous versions (2021 and 2022) contained highly controversial provisions and were withdrawn from further procedure following public pressure. After that, several meetings were held between representatives of the Ministry of the Interior and civil society representatives within the framework of Working Group 24 of the National Convention on the European Union. Since May 2023, the participants in this dialogue—previously assessed as a good practice—have not been informed about any further work on the Draft. Relating to the abovementioned dialogue, the MoI invited the National Convention on the European Union (NCEU) for three-day consultations in August 2025, during holiday season and with short notice. Although the Ministry agreed to postpone the meeting, NCEU declined the invitation, arguing that police conduct during ongoing protests cast doubt on the very objectives of adopting the new law, as outlined in the Reform Agenda of the Republic of Serbia; therefore, any dialogue on a new law would be futile until these practices are rectified and the consistent application of existing legislation is guaranteed. The Decision on the establishment of the Working Group set January 31, 2025 as the deadline for drafting the Law; however, no working text has been published to date (March 2026). A working version from August 2025 was submitted to the National Convention on the European Union. Subsequently, the public was informed that draft versions of laws within the competence of the Ministry of the Interior—including the Draft Law on Internal Affairs—were presented to members of the parliamentary Committee at a special meeting held on February 2, 2026, outside the regular legislative procedures. |
| Analyse how key principles of RGF were respected in the reform step implementation | How transparent has the reform step implementation been? How has civil society and the wider public been informed about it? What data and information, including key documents, have been made publicly available? How inclusive was the implementation process? Has the implementation of the reform step allowed for participation of interested stakeholders, especially civil society organisations and – where applicable – business community? How was such participation ensured? What were the issues regarding their participation, if any? Depending on the reform step, provide an analysis of how other key RGF principles – apart from transparency and inclusivity analysed above – were respected in its implementation, as applicable: sound financial management, equal treatment, non-discrimination and proportionality for intended purpose. Please provide references wherever possible. Transparency Apart from the announcement on the official e-Consultations website regarding the drafting of a new law and the publication of the Decision on the establishment of the Working Group with its composition, there has been no further public information about the process. As described above, there have been serious delays in taking the subsequent formal steps in the procedure. The Ministry did approach the National Convention on the European Union (NCEU) for consultations on the working version and provided a draft document on that occasion; however, this was done in an inappropriate manner and in a context that undermined any stated good intentions for reform. Moreover, referring to the moratorium on cooperation with the highest representatives of the Government, in place since February 2025, the NCEU did not wish to engage in dialogue with the Ministry of the Interior as a somehow privileged party. Instead, it announced that it would participate in a public debate open to all interested stakeholders, once such a debate is launched. The Government of the Republic of Serbia and the Ministry of the Interior are expected to ensure the general conditions necessary for conducting any kind of dialogue. Inclusivity Inclusivity was not ensured in the steps taken so far. The Working Group consists only of representatives of MoI, among which also police unions have been represented. Civil society organisations have not been invited to participate. When they were approached in August 2025, it was late, untimely and pro forma (please see key issues in implementation above). |
| Public availability of evidence of implementation | Has the final source of verification (as per Reform Agenda) been made publicly available? If yes, please list the source (provide link) and date. The final source of verification is not available, because the measure has not been implemented – Law has not been adopted thus far. Publicly available documents: - Announcement of drafting the Law on Internal Affairs - Decision on the establishment of the Working Group Link: https://ekonsultacije.gov.rs/topicOfDiscussionPage/427/3 (last accessed 25/02/2026) Date stamp: 14/11/2024 |
| Analyse quality of the final output of the reform step | To what extent does the final output of this reform step respect the applicable EU membership requirements/principles/standards? The final output of the reform step has not been provided thus far. The analysis of the working version that has been shared with the NCEU in August 2025 leads to several conclusions: The structure of the law has been improved, and its length reduced — from 362 articles in the previous draft to 287 articles. The operational independence of the police vis-à-vis the Ministry of the Interior is formally guaranteed; however, no mechanisms are envisaged to ensure that this independence is upheld in practice. Similarly, the operational independence of the Internal Control Sector is prescribed; however, the Minister continues to exercise significant influence over the work of this sector. No mechanisms were envisaged to ensure that the police comply with prosector’s orders – a long-standing problem of the prosecutorial investigation in Serbia, recently exacerbated in practice. The provisions on the prevention of torture have been improved, but not fully in line with the CPT recommendations. For example, there is no provision that would introduce systematic audio-video recording of all police interviews to increase transparency and accountability. A novelty is the provision establishing a special commission aimed at improving police conduct from the perspective of torture prevention. It is envisaged that a representative of the public will participate in the work of this commission and that the commission may initiate disciplinary proceedings. However, its composition, organization, tasks, and working methods are to be determined by the Minister, which leaves excessive discretion in the hands of the Minister. The CPT recommendation concerning the specialization of prosecutors in the field of torture relates goes beyond the scope of this particular law. In the previous Draft version (2022), the sound cannon and instant restraint devices were added to the list of means of coercion, then removed after pressure from civil society. In the new Draft (2025) they have not been added back. However, rubber bullets were kept in the list, and envisaged to be used against both individuals and groups, which remains highly dangerous and problematic. The working version of Draft Law has only partially addressed GRECO recommendations. For example, the criticized provision enabling a second term for the police director without public competition procedure was retained. This working version again raises concerns about reducing transparency and oversight of the MoI and police work. |

# Final assessment

| Assess formal achievement | Not achieved |
| --- | --- |
| Elaboration of final assessment | Only three of the necessary steps to fulfil this measure have been conducted, with deficient transparency and no inclusivity. Overall assessment of MoI and police practice in parallel to the work on drafting the law indicates that there is no intention by the authorities to effectively ensure operational independence of the police and to improve track-record regarding police brutality and prevention of torture, as put forward by the Reform Agenda. |

Read more in the sections on the prohibition of torture and police reform in the prEUgovor Alarm Reports of May 2025 and November 2025. The last annual report of the National Prevention Mechanism Against Torture has been published for 2024. The last published CPT report for Serbia refers to the year 2023, so it couldn’t be used to evaluate recent practice.