Reform step monitoring template

- Step overview

| Sub-area | 9.3. Fight against organized crime |
| --- | --- |
| Reform | 9.3.1. Tackling of organized and serious crime |
| Reporting indicator | Status of organised and serious crime related legislation and its implementation |
| Reform Step | 3. Adoption of operational plan on financial investigations |
| Step deadline | December 2025 |
| Step value in EUR | 3.396.905,84 |
| Responsible | Ministry of justice |
| Baseline | Currently there is no any strategic framework covering the financial investigations in Serbia |
| Sources of verification | Official Gazette of the Republic of Serbia |

- Analysis

| Define step milestones | For each step, based on the provisions of the Reform Agenda, define several key milestones for full achievement and number them. E.g. for a legislative step, that can include: 1. Announcement of the work on the new law, 2. Setting up a working group, 3. Initial consultation (via eConsultation portal), 4. Publication of all key materials on eConsultation portal (draft law, RIA, consultation report), 5. Public debate in accordance with the Rules of Procedure of the Government, 6. Adoption in Parliament (with analysis of the adoption procedure). Depending on the reform step, make sure that milestones take into account applicable legal requirements (e.g. Law on the Planning System, Government Rules of Procedure, etc.). - Setting up the working group in an open and transparent process - The working group jointly formulates the proposed plan through the participation and consensus of all its members - Publication of the draft on eConsultation Portal - Public debate conducted with minimum duration of 20 working days - Consultation and public debate report(s) published on eConsultation Portal, along with final draft version - The Plan adopted by the Government - Publication in the Official Gazette |
| --- | --- |
| Analyse achievement of each milestone | For each identified milestone, provide a succinct analysis of its implementation process. Use numbered points corresponding to the defined milestones above. Please provide references wherever possible. - The Working Group was established on an unknown date, likely in 2025, by a decision of the Minister of Justice. The appointment process was not transparent, and the composition of the Working Group became publicly known only when the proposed plan was published on the e-Consultation platform. The following institutions were represented in the Working Group: - Directorate for Management of Seized Property - Supreme Court - Supreme Public Prosecutor - Public Prosecutor for Organised Crime - Directorate of Criminal Police - Directorate for the Prevention of Money Laundering - Customs Administration - Tax Administration - Agency for the Prevention of Corruption - Ministry of Finance - National Bank of Serbia - Agency for Business Registers - Republic Geodetic Authority - Republic Directorate for Property - No further information regarding the Working Group is publicly available. - The Ministry of Justice published an announcement marking the start of the process on 22 August 2025, and the draft plan on 22 October 2025. The draft was open for public consultation between 22 October 2025 and 11 November 2025, a total of 20 days (less than 20 working days). - Reports on the consultation and public debate are not published on the e-Consultation portal, nor is the final draft version available. - The Plan has not been adopted by the Government or the Ministry. - Not applicable. |
| Key issues in implementation | List and briefly explain key problems/issues arising in the reform step implementation. This can follow the milestone structure, but depending on the reform step, it can also be an analysis for the whole step. Please provide references wherever possible. It is totally unclear what the legal status of this document would be within the planning system of the Republic of Serbia, as “operational plan” is not recognised there. Similarly, it is still unknown who will adopt the act. The Working Group did not include representatives of CSO or academia. Although the public consultation process concluded long ago, no final version of the document or report on the consultation has been published. The plan includes a number of potentially useful measures, but it also contains deficiencies, particularly with regard to inter-institutional cooperation. |
| Analyse how key principles of RGF were respected in the reform step implementation | How transparent has the reform step implementation been? How has civil society and the wider public been informed about it? What data and information, including key documents, have been made publicly available? How inclusive was the implementation process? Has the implementation of the reform step allowed for participation of interested stakeholders, especially civil society organisations and – where applicable – business community? How was such participation ensured? What were the issues regarding their participation, if any? Depending on the reform step, provide an analysis of how other key RGF principles – apart from transparency and inclusivity analysed above – were respected in its implementation, as applicable: sound financial management, equal treatment, non-discrimination and proportionality for intended purpose. Please provide references wherever possible. Key issues It is unclear what the legal status of this document would be within the planning system of the Republic of Serbia. Specifically, there is no provision for such a type of document under the Law on the Planning System of the Republic of Serbia. In the Reform Agenda, the Ministry of Justice is designated as the responsible authority. In the draft document that was opened for public consultation, it was titled “Operative Plan to Conduct Financial Investigation and Confiscation of Property Related to Criminal Offences for the Period 2026–2028”. However, within the text, it is occasionally referred to as a “strategy”. In this context, it is necessary to clarify whether the document is intended to constitute a strategy, which would require adoption by the Government of Serbia and thus be procedurally appropriate, or another type of planning document subject to adoption by the Ministry of Justice. Although the public consultation process concluded more than four months ago, no final version of the document or report on the consultation has been published. According to unofficial sources, the document is currently under revision by the European Commission. The plan includes a number of potentially useful measures, but it also contains deficiencies, particularly with regard to inter-institutional cooperation. While “memorandums of understanding” are envisaged, a clear legal obligation for cooperation already exists under applicable laws. Furthermore, the draft refers to other draft documents that have not been adopted, such as the Action Plan for the Anti-Corruption Strategy 2026–2028. Transparency The draft document exists; however, not all of the analyses on which it is based are publicly available. As a result, it is not fully possible for members of the public to understand which legislative and practical measures are necessary to address the issues identified in the Operative Plan. Inclusivity It appears that the Working Group included representatives from most relevant public institutions. However, members of the public, including civil society organisations and the academic community, were not involved in the drafting phase. The document was posted on the e-Consultation portal, but no information on the outcome of the consultation has been made available. |
| Public availability of evidence of implementation | Has the final source of verification (as per Reform Agenda) been made publicly available? If yes, please list the source (provide link) and date. Not applicable. |
| Analyse quality of the final output of the reform step | To what extent does the final output of this reform step respect the applicable EU membership requirements/principles/standards? Not applicable |

- Final assessment

| Assess formal achievement | Not achieved. |
| --- | --- |
| Elaboration of final assessment | Draft exists, but it is not adopted yet. |

https://ekonsultacije.gov.rs/topicOfDiscussionPage/553/1, Draft act, pages 2 and 3.

https://ekonsultacije.gov.rs/topicOfDiscussionPage/520/3

https://ekonsultacije.gov.rs/topicOfDiscussionPage/553/1

https://ekonsultacije.gov.rs/topicOfDiscussionPage/553/1 , e.g. on pages 13 and 16.

Partial achievement possible only for quantitative steps. For such steps, insert level (percentage) of implementation, if available.