- Step overview

| Sub-area | 9.5: Fight against corruption |
| --- | --- |
| Reform | 9.5.1. Improved fight against and prevention of corruption |
| Reporting indicator | Status of fight against and prevention of corruption related regulatory Framework |
| Reform Step | 2. All vacant positions for prosecutors and judges in anti-corruption departments and in special prosecutor’s office for organised crime, and special department of the higher court and of the appellate court in Belgrade for organised crime are filled in accordance with the Annual Schedule of Judges (adopted by the HJC) and the Decision of the High Prosecution Council on the number of public prosecutors and trained. |
| Step deadline | December 2025 |
| Step value in EUR | 13.587.623,37 |
| Responsible | HPC, HJC |
| Baseline | No. of employees in special departments for Suppression of Corruption within the High Prosecution Offices Beograd – 9, Novi Sad – 12, Niš – 9, Kraljevo – 6. No of employees in special departments for Suppression of Corruption in the High Courts Beograd – 4, Novi Sad – 6, Niš – 5, Kraljevo – 6. Prosecutors Office for Organised Crime has 22 public prosecutors. Special Department of the Appellate Court in Belgrade has 11 judges. |
| Sources of verification | Annual report of HPC Annual report of HJC |

- Analysis

| Define step milestones | For each step, based on the provisions of the Reform Agenda, define several key milestones for full achievement and number them. E.g. for a legislative step, that can include: 1. Announcement of the work on the new law, 2. Setting up a working group, 3. Initial consultation (via eConsultation portal), 4. Publication of all key materials on eConsultation portal (draft law, RIA, consultation report), 5. Public debate in accordance with the Rules of Procedure of the Government, 6. Adoption in Parliament (with analysis of the adoption procedure). Depending on the reform step, make sure that milestones take into account applicable legal requirements (e.g. Law on the Planning System, Government Rules of Procedure, etc.). - The Annual Schedule of Judges, adopted by the High Judicial Council (HJC), provides for the same or an increased number of judges. - The decision of the High Prosecutorial Council (HPC) on the number of public prosecutors provides for the same or an increased number of prosecutors. - Public calls have been issued for all vacant posts in Public Prosecutor’s Office (PPO) units. - The High Prosecutorial Council adopts decisions in a timely manner for all vacant posts in PPO units. - Pending decisions of the High Prosecutorial Council, all vacant posts in Prosecutor’s Offices for Organised Crime (POC) are continuously filled through temporary transfers from other PPOs. - All judges and prosecutors have completed the training necessary for work in anti-corruption units. |
| --- | --- |
| Analyse achievement of each milestone | For each identified milestone, provide a succinct analysis of its implementation process. Use numbered points corresponding to the defined milestones above. Please provide references wherever possible. - Although the Reform Agenda step seeks to ensure an adequate number of judges in anti-corruption departments through the “Annual Schedule of Judges, adopted by the High Judicial Council (HJC)”, this is contrary to the powers of that body. Specifically, the Annual Schedule of Judges is adopted by each court president. In these terms, the Reform Agenda step, as currently defined, cannot formally be achieved unless the relevant legislation (notably the Law on the Organisation of Courts) is amended in advance. As regards the substantive situation, it is as follows: The President of the Belgrade Appellate Court adopted the Annual Schedule of Judges for 2026 on 6 November 2025, with subsequent amendments on 30 December 2025. In the two court councils responsible for appeals in cases of organised crime, the court president scheduled a total of 12 judges (baseline: 11). In the Annual Schedule for 2025, adopted on 31 October 2024, the number of judges was the same as the baseline (11) . Amendments to the Schedule, made on 25 June 2025, established the current number of judges. The Higher Court of Belgrade’s Annual Schedule envisages no changes compared with the baseline, as reflected in the decision of 31 October 2025 for the year 2026 (4 judges). The Higher Court of Novi Sad, in its Annual Schedule for 2026, envisages five judges in the units responsible for anti-corruption, which is fewer than the baseline of six. The Higher Court of Niš, in its Annual Schedule for 2026, adopted on 31 October 2025, envisages six judges in the unit responsible for anti-corruption, which is higher than the baseline of five. The Higher Court of Kraljevo has not published its Annual Schedule for 2026. The Schedule for 2025, adopted on 31 October 2024, envisaged the same number of judges in the anti-corruption department as the baseline (six) . However, following amendments to the Schedule, adopted on 2 December 2024, the number of judges was reduced to five. Please note that the statistics presented here include only trial judges in court councils and do not cover judges involved in pre-trial investigations or decisions on detention, in order to maintain comparability with the baseline. - Decision of the High Prosecution Council on the number of public prosecutors was not changed in 2025 or 2026. The decision of the High Prosecutorial Council (HPC) on the number of public prosecutors was not amended in 2025 or 2026; therefore, the decision adopted on 31 October 2023 remains in force. However, similarly to the situation with courts and judges, the Reform Agenda step may not be fully achievable through amendments to the decision issued by the relevant Council. While the envisaged number of prosecutors is directly regulated by the decision in the case of the Prosecution for Organised Crime, this is not the case for prosecutors working on corruption cases in higher prosecution offices. Their number is determined by the Head Prosecutors within the framework of the Annual Schedule. With regard to the Prosecution for Organised Crime (POC), out of 25 envisaged positions, the actual number of public prosecutors is 10. There is no official information on the actual number of prosecutors, either in the Prosecution for Organised Crime (POC) or in the anti-corruption units of the Higher Prosecutors’ Offices (HPPs). The High Public Prosecutor’s Office has not yet published its annual report for 2025. Annual Schedules are not available on PPO websites, and the Informative Directory of the POC is outdated. Similarly, the Informative Directories of the HPPs in Belgrade, Novi Sad, and Kraljevo do not contain this information. Furthermore, in the case of the HPP in Niš, the document is outdated. According to media reports, following amendments to the Law and voting in HPC sessions in early March, the POC, in addition to the 10 permanently assigned prosecutors, has six prosecutors (out of the previous 11) temporarily assigned from other prosecution offices, against a total of 25 envisaged positions. The situation in other HPPs, according to the unofficial information is as follows: - Belgrade: 19 prosecutors assigned; 25 envisaged - Niš: 8 prosecutors assigned; 13 envisaged - Kraljevo: 12 prosecutors assigned; 15 envisaged - Novi Sad: 12 prosecutors assigned; 15 envisaged If these figures are correct, the actual number of prosecutors exceeds the baseline. However, this is unlikely and is more probably a consequence of differences in counting methods, specifically whether prosecutors temporarily assigned from other PPO offices are included or not. Based on data published on the website of the High Prosecutorial Council, a total of 20 prosecutors are assigned to the special anti-corruption department in the Higher Prosecutors’ Office in Belgrade, 12 in Novi Sad, 11 in Kraljevo, and 9 in Niš. - The High Prosecutorial Council (HPC) opened a public call for the election of nine prosecutors in the Prosecution for Organised Crime (POC) on 31 December 2024. While some vacancies exist in the Higher Public Prosecutors’ Offices (HPOs), it is unclear to what extent the employment of new prosecutors would be linked to the work of the anti-corruption departments. - This process has not yet been finalised. - The Prosecution for Organised Crime (POC) did not reach full employment of the envisaged number of prosecutors, even when those temporarily assigned from other offices are included in the statistics during this period. On 28 January 2026, the Parliament adopted amendments to the Law on Public Prosecution, based on a proposal by its member Uglješa Mrdić (SNS), together with several other judicial laws. The procedure and content of these laws were heavily criticised both domestically and by the European Commission’s representatives. This prompted a request for the Venice Commission to assess the amended laws, which the Commission accepted. Among other changes, Article 69 of the Law was amended so that the High Prosecutorial Council (HPC), rather than the Highest Public Prosecutor, would assign prosecutors to temporary positions in the POC. While this provision is generally in line with international standards, in the context of a decision-making process in the HPC that was effectively blocked due to the high majority required for decisions and conflicting interests among its members, it was evident that this amendment could significantly slow down necessary assignments. Additionally, the Law’s transitional provisions envisaged that all prosecutors temporarily assigned to the POC by the Highest Public Prosecutor would be returned to their home offices within 30 days (i.e., by 9 March 2026). It is noteworthy that this change was not presented by the original proponent (Mrdić) but was introduced as an amendment by another SNS MP during the parliamentary debate. Since amendments are not published on the parliamentary website, this substantial provision, directly affecting the work of the POC, was not publicly available. - The Reform Agenda does not specify the type of training expected for judges and prosecutors. Where data on trainings exist, they are not presented specifically for judges and prosecutors in the units responsible for anti-corruption. However, given that the overall number of judges and prosecutors has not increased—or has not increased significantly—the issue of training appears to be of secondary importance. |
| Key issues in implementation | List and briefly explain key problems/issues arising in the reform step implementation. This can follow the milestone structure, but depending on the reform step, it can also be an analysis for the whole step. Please provide references wherever possible. |
| Analyse how key principles of RGF were respected in the reform step implementation | How transparent has the reform step implementation been? How has civil society and the wider public been informed about it? What data and information, including key documents, have been made publicly available? How inclusive was the implementation process? Has the implementation of the reform step allowed for participation of interested stakeholders, especially civil society organisations and – where applicable – business community? How was such participation ensured? What were the issues regarding their participation, if any? Depending on the reform step, provide an analysis of how other key RGF principles – apart from transparency and inclusivity analysed above – were respected in its implementation, as applicable: sound financial management, equal treatment, non-discrimination and proportionality for intended purpose. Please provide references wherever possible. Key issues Transparency While some aspects of the process are transparent, such as the public call for new prosecutors, the main issue is that most information is not published, particularly regarding the Higher Prosecutors’ Offices (e.g., their Annual Schedules). Furthermore, the Reform Agenda step lacks clarity regarding the baseline—specifically, whether it tracks only the number of trial judges and whether it includes only permanent prosecutors or also those temporarily assigned. It is therefore of utmost importance to resolve these ambiguities and to ensure the transparency and accuracy of all relevant sources of information. In the process of legislative changes affecting the achievement of this reform step, transparency existed to a certain extent but was limited by the fact that the key provision was introduced as an amendment by a Member of Parliament and was therefore not published on the parliamentary website. Inclusivity The process for preparing the Annual Schedule in courts and prosecution offices provides for some level of inclusiveness for those directly concerned. The Decision on the overall number of prosecutors in the Prosecution for Organised Crime (POC) was not changed. The legislative process for amending the relevant laws disregarded the principle of inclusivity. Neither the High Judicial Council (HJC) nor the High Prosecutorial Council (HPC) were consulted on the proposed amendments. Similarly, there was no consultation with the Agency for the Prevention of Corruption, professional associations, or the broader public. Regarding the draft laws, the Government provided a positive opinion. However, due to parliamentary procedure, for amendments proposed during the debate, the Government was not consulted and only the original proponent of the bills (MP Mrdić) was involved. Likewise, the European Commission was not consulted prior to the adoption of the set of judicial laws, despite their significance in the context of Chapter 23 of EU integration. |
| Public availability of evidence of implementation | Has the final source of verification (as per Reform Agenda) been made publicly available? If yes, please list the source (provide link) and date. The sources of verification indicated in the Reform Agenda are generally incorrect, except partially in the case of the Prosecution for Organised Crime (POC). Substantively, some sources of verification are available, such as the Annual Schedules of courts, while others, such as the Annual Schedules of Higher Prosecutors’ Offices (HPOs), are missing. The actual number of POC prosecutors is not readily available but can be determined by consulting multiple sources. For these links, please see in “Analyses” of milestones. |
| Analyse quality of the final output of the reform step | To what extent does the final output of this reform step respect the applicable EU membership requirements/principles/standards? The reform step has not been achieved. |

- Final assessment

| Assess formal achievement | Not achieved. |
| --- | --- |
| Elaboration of final assessment | The reform step is neither correctly nor clearly formulated. Nevertheless, it is evident that the goals of the reform were not achieved, as the number of envisaged judges and prosecutors did not reach the planned levels and, in some instances, did not improve compared with the baseline. Furthermore, as a consequence of recently amended legislation, the number of prosecutors assigned to the Prosecution for Organised Crime (POC) has even decreased compared with the situation at the beginning of the process. This deterioration appears to have been motivated by interests clearly at odds with the goals of the reform and with overall EU integration, namely the aim of preventing potential investigations of corruption against individuals in government or closely associated with it. |

https://bg.ap.sud.rs/files/GODIŠNJI%20RASPORED%202026..pdf, page 16.

https://www.bg.ap.sud.rs/files/GODISNJI%20RASPORED%20ZA%202025.%2028.10.2024..pdf, page 15.

https://www.bg.ap.sud.rs/files/IZMENE%20GODIŠNJEG%20RASPOREDA%2025.6.%202025..pdf, pages 2 and 3.

https://www.bg.vi.sud.rs/tekst/320/sudije.php

https://www.ns.vi.sud.rs/files/Godišnji%20raspored%20poslova%20za%202026.%20godinu.pdf, page 7.

https://www.ni.vi.sud.rs/files/GODISNJI%20RASPORED%202026%201.pdf, page 6.

https://www.kv.vi.sud.rs/files/Godisnji2025.pdf, page 12.

https://www.kv.vi.sud.rs/files/Su%20I%202-36-24.pdf, page 1.

https://vst.jt.rs/wp-content/uploads/2024/09/Odluka-o-broju-javnih-tuzilaca-u-javnim-tuzilastvima.pdf

https://vst.jt.rs/1206-2/

Годишњи извештај о раду јавних тужилаштава | Информације о раду | RJT

https://tok.jt.rs/html_tok/pocetna/informator_cir.pdf

https://informator.poverenik.rs/informator?org=vNWkyhfW9Fe8SNxX8&ch=B7e85r4rMtMRMyzb7&code=

https://informator.poverenik.rs/informator?org=TEKpsq2CscruX7kRu&ch=B7e85r4rMtMRMyzb7&code=

https://informator.poverenik.rs/informator?org=scgREq2vFPDmqWqzP&ch=B7e85r4rMtMRMyzb7&code=

https://informator.poverenik.rs/informator?org=337oQ4Ggkj3ntbrjY&ch=B7e85r4rMtMRMyzb7&code=

https://n1info.rs/vesti/osveta-vlasti-tuziocima-za-organizovani-kriminal-ireni-bjelos-i-aleksandru-isailovicu-odlaze-iz-tok-a-vecina-upucenih-tuzilaca-ostaje-ali-ne-duze-od-tri-godine/

https://vst.jt.rs/1206-2/

https://vst.jt.rs/wp-content/uploads/2024/12/Javni-konkurs-za-izbor-javnih-tuzilaca-sajt-1.pdf

www.parlament.gov.rs/upload/archive/files/cir/pdf/zakoni/14_saziv/2731-25.pdf

https://n1info.rs/vesti/rasprava-mrdicevi-zakoni-pravosudje-brnabic/

https://www.danas.rs/vesti/politika/zvanicnik-eu-mrdicevi-zakoni-nisu-u-skladu-sa-pristupnim-putem-srbije-eu-odloziti-njihovu-primenu/

https://radar.nova.rs/politika/venecijanska-komisija-u-beogradu/

https://www.transparentnost.org.rs/en/ts-and-media/press-isues/13005-harmful-consequences-of-changes-in-judicial-regulations-on-the-fight-against-corruption

Documents obtained from an MP, not published on parliamentary web-page.

Ibid.

https://www.youtube.com/watch?v=eC4g3tR-yC8