# Reform step monitoring template

# Step overview

| Sub-area | 6.2. Private sector development |
| --- | --- |
| Reform | 6.2.1. Enhanced investment and development opportunities for entrepreneurs and private sector – Public procurement |
| Reporting indicator | Degree of transparency of intergovernmental agreements |
| Reform Step | The level of transparency regarding all projects contracted under intergovernmental agreements is increased by introducing project-specific information on the website of the ministry in charge of implementing the project on any completed, ongoing and new procurement contracts under intergovernmental agreements. All contracts under intergovernmental agreements will be published starting from December 2024, and this practice will be maintained in the following years for all new contracts, including: name of the project; basic procurement contract information; contracting authority; main contractor and procurement procedure followed |
| Step deadline | June 2025 |
| Step value in EUR | 20.381.435,06 |
| Responsible | All line ministries in charge of the projects |
| Baseline | There is no obligation to publish project-specific information on contracts under intergovernmental agreements, however some project-specific information on contracts under intergovernmental agreements are published |
| Sources of verification | Websites of ministries in charge of project implementation - links to the projects of IGA in their competence for each ministry |

# Analysis

| Define step milestones | For each step, based on the provisions of the Reform Agenda, define several key milestones for full achievement and number them. E.g. for a legislative step, that can include: 1. Announcement of the work on the new law, 2. Setting up a working group, 3. Initial consultation (via eConsultation portal), 4. Publication of all key materials on eConsultation portal (draft law, RIA, consultation report), 5. Public debate in accordance with the Rules of Procedure of the Government, 6. Adoption in Parliament (with analysis of the adoption procedure). Depending on the reform step, make sure that milestones take into account applicable legal requirements (e.g. Law on the Planning System, Government Rules of Procedure, etc.). - Establishment of dedicated and publicly accessible sections/sub-sections on the websites of all competent ministries implementing projects under international agreements. - Publication of the information about the project and list of all ongoing and completed contracts concluded under international agreements starting from December 2024. - Publication of full contract texts and all contract annexes. - Regular updating of information on implementation. |
| --- | --- |
| Analyse achievement of each milestone | For each identified milestone, provide a succinct analysis of its implementation process. Use numbered points corresponding to the defined milestones above. Please provide references wherever possible. - Milestone related to the establishment of dedicated and publicly accessible sections/sub-sections on the websites of all competent ministries implementing projects under international agreements is achieved. The following ministries have dedicated sections/subsections related to the Projects - the Ministry of Finance, the Ministry of Mining and Energy, the Ministry of Construction, Transport and Infrastructure, the Ministry of Environmental Protection, and the Ministry for Public Investment. These ministries have been selected for assessment as they are currently competent authorities responsible for the implementation of major infrastructure and investment projects typically concluded under international (intergovernmental) agreements. - Publication of the information about the project and list of all ongoing and completed contracts concluded under international agreements starting from December 2024 – partially achieved. While dedicated sections exist in ministries’ websites, coverage is inconsistent and updates are uneven. There is no evidence of a harmonised or Government-wide approach. Ministries in most cases publish basic information including: project name, contracting authority, main contractor, procurement procedure, date of registration, project status (ongoing/completed). However, the interpretation of “basic information” is minimal and there is no unique approach in different institutions. It is important to note that there is no significant change in terms of new information provided compared to the pre-Reform Agenda situation. The websites of the following institutions have been examined: - The Ministry of Finance created a specific subsection under its website (Documents - Projects), publishing a document titled “Reform Agenda of the Republic of Serbia – Intergovernmental agreements and projects where the Ministry of Finance is an investor”; website visited on 3rd April 2026. - The Ministry of Mining and Energy created a specific subsection under its website (Public Interest - Projects under intergovernmental agreement); website visited on 3rd April 2026. - The Ministry of Construction, Transport and Infrastructure maintains a Projects section on the website, but but it contains inconsistent and non-standardized information across projects, lacks key data (such as financing and timelines), and does not clearly indicate their implementation status; website visited on 3rd April 2026. - The Ministry of Environmental Protection has on its website projects section that contains info on two projects and under the section documents for specific areas (e.g. protection of water) we can find section project where some reports are available. This makes difficult to obtain a comprehensive and structured overview of ongoing and completed projects; website visited on 3rd April 2026. - The Ministry for Public Investment has on its website projects sub-section under actualities. However, there is no list of projects with relevant information, but project-related information is presented through news-style updates, making it difficult to identify and review ongoing and completed projects; website visited on 3rd April 2026. - As regards publication of contracts this milestone is not achieved as on the examined websites there are no published contracts. In the specific case of the Novi Sad railway reconstruction, the Government published the main contract and four annexes following public pressure. However, this measure was not followed up for other projects. - Regular updating of information on implementation is mostly not provided so this milestone cannot be considered as achieved. There is no information or very limited on implementation progress (e.g. info is mostly classified as ongoing or completed), financial execution, amendments, and delays. |
| Key issues in implementation | List and briefly explain key problems/issues arising in the reform step implementation. This can follow the milestone structure, but depending on the reform step, it can also be an analysis for the whole step. Please provide references wherever possible. Normative ambiguity in the formulation of the reform step: The wording of the measure creates inconsistency between the statement that “all contracts will be published” and the subsequent limitation to selected elements of information. This leaves room for divergent interpretations regarding the scope of the disclosure obligation and has enabled a minimalist implementation approach. Fragmented and inconsistent institutional practice: although dedicated sections exist across relevant ministries, the scope, structure and level of detail of published information vary significantly, indicating the absence of a harmonised Government-wide approach. Minimalist publication of information and insufficient information of implementation progress: ministries predominantly publish only basic descriptive elements (project title, contractor, procedure, status), without status in implementation and contracts. Absence of full contract transparency: full contract texts and annexes are not systematically published. The only identified example (Novi Sad railway reconstruction) was disclosed under exceptional circumstances and does not reflect an institutionalised practice. Lack of transparency regarding contract modifications and subcontracting: there is no publicly available information on amendments, annexes, changes in scope or value, nor on subcontracting procedures and arrangements. Outdated or incomplete information in certain ministries: some websites have not been updated regularly, which undermines reliability and sustainability of the measure. Limited added value compared to the pre-Reform Agenda situation: the published information does not represent a substantial improvement in transparency compared to the situation prior to the adoption of the Reform Agenda. |
| Analyse how key principles of RGF were respected in the reform step implementation | How transparent has the reform step implementation been? How has civil society and the wider public been informed about it? What data and information, including key documents, have been made publicly available? How inclusive was the implementation process? Has the implementation of the reform step allowed for participation of interested stakeholders, especially civil society organisations and – where applicable – business community? How was such participation ensured? What were the issues regarding their participation, if any? Depending on the reform step, provide an analysis of how other key RGF principles – apart from transparency and inclusivity analysed above – were respected in its implementation, as applicable: sound financial management, equal treatment, non-discrimination and proportionality for intended purpose. Please provide references wherever possible. Transparency Overall, the transparency of the reform step implementation has been limited. While the Government reported the step as implemented in the second payment request (15 July 2025), the NCEU did not receive further information on how and when the step was achieved. Some improvements can be observed through new or dedicated web sections created by certain ministries (e.g. Ministry of Finance and Ministry of Mining and Energy), which likely relate to the Reform Agenda commitments. However, the content disclosed through these sections is generally minimal and appears to reflect a very narrow interpretation of the Reform Agenda obligations. Although certain ministries established dedicated sections and published basic project information, there is no evidence of a harmonised or Government-wide transparency framework. Information is fragmented across ministerial websites, with no centralised access point. Also, there was not systemic change related to the publishing of contracts - subcontracting contracts and information on subcontractor selection procedures were not published. Overall, while certain formal steps towards transparency have been undertaken, the implementation does not yet ensure comprehensive, consistent and proactive public disclosure in line with the intended objectives of the Reform Agenda and the RGF transparency principle. Inclusiveness (participation of stakeholders) The implementation process appears to have been weak in terms of inclusiveness, with no evidence of a structured mechanism enabling participation of civil society organisations or other interested stakeholders. Transparency Serbia submitted detailed comments regarding this Reform Step during the draft Reform Agenda phase, raising substantive concerns and proposing improvements. However, the comments were not addressed and the step wording was not revised, resulting in an ambiguous formulation being adopted. |
| Public availability of evidence of implementation | Has the final source of verification (as per Reform Agenda) been made publicly available? If yes, please list the source (provide link) and date. Yes partially, here are the links of the projects section on the websites of the relevant ministries: - The Ministry of Finance - The Ministry of Mining and Energy - The Ministry of Construction, Transport and Infrastructure - The Ministry of Environmental Protection - The Ministry for Public Investment However, as indicated above, the level of detail varies significantly across institutions, as there is no standardized approach to presenting project information, and the timeliness of updates is also inconsistent. |
| Analyse quality of the final output of the reform step | To what extent does the final output of this reform step respect the applicable EU membership requirements/principles/standards? The final output of this reform step only partially respects applicable EU membership requirements and public procurement principles. While the reform step formally aims to increase transparency of contracts concluded under intergovernmental agreements, which is directly relevant for alignment under Chapter 5 (Public Procurement), its design and implementation reveal significant ambiguities that limit its substantive alignment with EU standards. The wording of the reform step states that “all contracts under intergovernmental agreements will be published”, but it simultaneously narrows the obligation to the publication of selected elements (project name, basic procurement contract information, contracting authority, main contractor and procurement procedure followed). This ambiguity has allowed for a minimalist interpretation in practice, whereby ministries publish only limited descriptive information without systematically disclosing full contracts, annexes, amendments, financial data or subcontracting arrangements. As a result, the final output does not fully ensure: - transparency in line with EU public procurement principles, - effective public scrutiny of contract modifications, - demonstration of a track record of a fair and transparent procurement system, as required under EU accession benchmarks. Moreover, the reform step does not address the broader structural issue of derogations from the Public Procurement Law through international agreements, nor does it introduce safeguards ensuring compatibility of such practices with EU acquis principles. In conclusion, although the reform step contributes to a limited formal increase in transparency, the ambiguity in its formulation and the narrow scope of implementation prevent it from ensuring substantive compliance with EU membership requirements. Further clarification of obligations and expansion of disclosure standards would be necessary to achieve full alignment with EU public procurement standards. |

# Final assessment

| Assess formal achievement | Not achieved |
| --- | --- |
| Elaboration of final assessment | The reform step is not achieved. While certain ministries have established dedicated web sections and published limited project-specific information, the implementation remains fragmented and inconsistent. The published data is largely confined to basic descriptive elements, without systematic disclosure of full contracts, annexes, financial information or subcontracting arrangements. Moreover, ambiguities in the wording of the reform step have allowed for a minimalist interpretation of disclosure obligations, resulting in a formal rather than substantive increase in transparency. As a result, the measure does not yet ensure comprehensive and harmonised transparency in line with the intended objectives of the Reform Agenda and relevant EU public procurement standards. |